## Gen - Sched 1
SOUTH AFRICAN NATIONAL BIODIVERSITY INSTITUTE
KAROO DESERT NATIONAL BOTANICAL GARDENS: RING ROAD UPGRADE, GRAVEL SERVICE ROAD UPGRADE AND STROMWATER MANAGEMENT
SCHEDULE OF QUANTITIES
General Conditions of Contract for Works of Civil Engineering Construction (GCC 2015: 3rd Edition)
NB | TENDERERS MUST COMPLETE THE SCHEDULE OF QUANTITIES IN BLACK INK
SCHEDULE NO 1: GENERAL
PAYMENT | ITEM |  |  |  | UNIT | QUANTITY | RATE | AMOUNT
REFERS | NO |  |  | DESCRIPTION
TO
SANS | 100 | GENERAL
1200 A
| 101 | Scheduled fixed-charge and value-
related items:
PSA 8.3.1 |  | .01 | Fixed and Value-related preliminary and general charges |  | - | - | sum
| 102 | Scheduled time-related items:
PSA 8.4.1 |  | .01 Time-related preliminary and
|  |  | general charges |  | months | 12
PSA 8.8 |  | TEMPORARY WORKS
PSA 8.8.4 | 103 | Location and protection of existing
services:
|  | .01 | Water and sewer pipes |  | - | - | sum
|  | .02 | Electric and other cables |  | - | - | sum
|  | .03 | Supply and erecting of Sectional Fence |  | m | 50
| 104 | Accommodating traffic and maintaining temporary deviations |  |  | km | 1.2
| 105 | Temporary traffic-control facilities
|  | .01 | Flagman |  | man-days | 350
|  | .02 | Portable STOP and GO signs |  | number | 4
|  | .03 | Road signs, R- and TR-series |  | number | 4
|  | .04 | Delineators |  | number | 40
|  | .05 | Traffic cones |  | number | 40
|  | .06 | Safety jackets for use by SANBI officials and engineers |  | number | 10
Carried forward
Brought forward
PSA 8.6 | 106 | Prime cost sums:
|  | .01 | Housing for Engineer's representative |  | - | PC | sum | 45000
|  | .02 | Charge required by Contractor on
|  |  | subitem .01 above |  | % | 45000 | _____%
|  | .03 | Housing for Engineer inspections |  | - | PC | sum | 36000
|  | .04 | Charge required by Contractor on
|  |  | subitem .03 above |  | % | 36000 | _____%
OCCUPATIONAL HEALTH AND SAFETY
| 107 | Full time attendance on site of a SACPCMP-registered construction health and safety officer or manager from the start of construction until the end of project handover. |  |  | months | 12
|  | .01 | General
|  |  | .01 | First aiders and first aid kits. | - | - | sum
|  |  | .02 | Medical certificates of fitness Medical examination of all employees and certification of fitness by an occupational medicine practitioner. Pre-employment, annual and exit medical examination is required. | - | - | sum
|  |  | .03 | Emergency Equipment based on the risk exposure and emergency rescue. stretchers, neck brace, spill kits, lifting and lowering hosting equipment of the injured. | - | - | sum
|  |  | .04 | Competent inspectors for equipment such as examples scaffolding inspectors and lifting machine inspector. | - | - | sum
|  |  | .05 | Mandatory training such as risk assessments, legal liability/OHS Act, incident investigation. | - | - | sum
Carried forward
Brought forward
|  |  | .06 | Provide, supply and maintenance for each worker the following SANS approved personal protective equipment & clothing as per the site-specific risk assessments: • Hard Hats • Overall/work suit (100% Cotton) • Safety boots/shoes (Steel-Toe) • Safety gumboots (Steel-Toe) • Ear Plugs/Muffs • Dust Mask(at least FF2 type) • Respirators • Safety goggles • Hand gloves •Reflector vests • Other | - | - | sum
|  |  | .07 | Barricading and hoarding for fall arrest, SANS approved safety netting (orange color with minimum of 1,2 meters high). | - | - | sum
|  |  | .08 | Waste bins on site and regular removal. | - | - | sum
|  |  | .09 | Construction signage, including the sign for the construction work permit number. | - | - | sum
|  |  | .10 | Safe lifting equipment for lifting and lowering pipes. | - | - | sum
|  |  | .11 | Dust control measure for the prevention of dust nuisance. | - | - | sum
| 108 | TEMPORARY FENCING TO CORDEN OFF WORKS BETWEEN THE VARIOUS SECTIONS
|  | .01 | Bonnox fencing with shade cloth:
|  |  | .01 | 1,83m High 'Bonnox Close Mesh 1472/12' fence fixed to and including 150mm diameter gumpole posts at 5,0m centres cast in suitable sized concrete bases and the fence covered with shadecloth, including excavations, formwork, backfilling, cart away etc., installed complete. | m | 50
|  |  | .02 | Carefully take down and re-erect 1,83m High 'Bonnox Close Mesh 1472/12' fence fixed to and including 150mm diameter gumpole posts at 5,0m centres cast in suitable sized concrete bases and the fence covered with shadecloth including excavations, formwork, backfilling, cart away etc., installed complete. | m | 50
Carried forward
Brought forward
|  |  | .03 | Take down and remove 1,83m High 'Bonnox Close Mesh 1472/12' fence fixed to and including 150mm diameter gumpole posts at 5,0m centres cast in suitable sized concrete bases and the fence covered with shadecloth, gates etc., including making good. | m | 50
|  |  | .04 | 4500mm x 1830mm High Vehicle gate covered with shade cloth including gate posts, 3500mm x 1200mm High vehicle gate including gate posts, including excavations, formwork, backfilling, cart away etc., installed complete. | No | 2
|  |  | .05 | Carefully take down and re-erect 4500mm x 1830mm High Vehicle gate covered with shade cloth including gate posts, 3500mm x 1200mm High vehicle gate including gate posts, including excavations, formwork, backfilling, cart away etc., installed complete. | No | 2
| 109 | Contingency Allowance
|  | .01 | Provide the sum of R 300 000.00 (Three Hundred Thousand Rand) for contingencies, to be used as instructed for by the Engineer. |  | - | PC | sum | 300000
|  | .02 | Charge required by Contractor on sub item .01 above |  | % | 300000 | _____%
|  | .03 | Provide the sum of R 100 000.00 (One Hundred Thousand Rand) for surveyor, to be used as instructed for by the Engineer. |  | - | PC | sum | 100000
|  | .04 | Charge required by Contractor on sub item .03 above |  | % | 100000 | _____%
|  | .05 | Provide the sum of R 30 000.00 (Thirty Thousand Rand) for detail drawings from surveyor measurements, to be used as instructed for by the Engineer. |  | - | PC | sum | 30000
|  | .06 | Charge required by Contractor on sub item .05 above |  | % | 30000 | _____%
TOTAL SCHEDULE NO 1 CARRIED TO SUMMARY

## Schedule 2
SCHEDULE NO 2: ROADS AND STORMWATER DRAINAGE
PAYMENT | ITEM |  |  |  | UNIT | QUANTITY | RATE | AMOUNT
REFERS | NO |  |  | DESCRIPTION
TO
SANS 1200 |  | DEMOLITIONS
| 201 | Breaking up excavating and removing
|  | .01 | Remove 25mm Asphalt layer on existing roads and spoil to identified spoil site |  | m² | 9169
|  | .02 | Remove existing base layer to a depth of 200mm and remove to spoil site |  | m² | 9610
|  | .03 | Remove existing sub-base layer to a depth of 150mm and remove to spoil site |  | m² | 10742.8
|  | .04 | Extra over excavation for excavation in Intermediate material |  | m3 | 161.142
|  | .05 | Extra over excavation for excavation in hard rock material |  | m3 | 161.142
|  | .06 | Remove existing kerbing and spoil to identified spoil site |  | m | 2806
|  | .07 | Saw-cut into top of existing asphalt to facilitate part removal thereof. |  | m | 58
|  | .08 | Remove existing 450mm half-round concrete channel next to asphalt ring road and spoil to spoil site |  | m | 1080
CA.04.01 | 202 | Surface Preparation
|  | .01 | Trim and level off surface of ground (excavated or filled under this contract) to receive concrete surface beds,paving etc. including excavating or filling, ripping and scarifying as necessary and compacting the whole area for a depth of 150mm to a density of at least 93% Mod. AASHTO maximum density, part to falls. |  | m² | 9473
SANS 1200 |  | EARTH FILLING
| 203 | Earth filling supplied by the contractor under paving
|  | .01 | Import G7 subbase course material in accordance with SABS 1200 DM compacted to 93% Mod AASHTO density. |  | m3 | 301.2
Carried forward
Brought forward
|  | .02 | Import G5 subbase course material in accordance with SABS 1200 DM compacted to 95% Mod AASHTO density. |  | m3 | 1611.42
|  | .03 | Import C4 cemented natural gravel material (G5) from commercial sources and construct 125mm thick base compacted in accordance with SABS 1200 DM compacted to 98% Mod AASHTO density. |  | m3 | 1184.125
CA.03.06 | 204 | Extra over for stabilising C4 layer as in point .03 above with 3% cement
|  | .01 | Cement |  | t | 78.1522
BOND AND INTERLOCKING CONCRETE BLOCK PAVERS
| 205 | 80mm Thick Type S-A approved precast concrete coloured interlocking paving blocks (colour to Engineer specification) in accordance with SANS 1058, laid to falls on and including 25mm thick sand layer with joints filled in with sand, compacted with a vibration compactor. Type: "Kirstenbosch paver"
|  | .01 | Paving to roads, parking areas etc. to falls |  | m² | 9473
|  | .02 | Extra over for straight edge blocks |  | m | 947.3
|  | .03 | Fair circular cutting and waste to paving. |  | m | 1894.6
CB.03.04 |  | CONCRETE KERBING
| 206 | Install new concrete kerbing:
|  | .01 | Cast in situ kerbing or edge restraint
of maximum depth 200 mm and
maximum width 300 mm:
|  |  | .01 | Radius up to 4 m | m | 40
|  |  | .02 | Radius over 4 m up to 20 m | m | 270
|  |  | .03 | Radius over 20 m and straight
|  |  |  | sections | m | 900
|  | .02 | Cast in situ kerbing of maximum depth
300 mm and maximum width 200 mm:
|  |  | .01 | Radius up to 4 m | m | 5
|  |  | .02 | Radius over 4 m up to 20 m | m | 35
|  |  | .03 | Radius over 20 m and straight
|  |  |  | sections | m | 168
Carried forward
Brought forward
CB.03.04 |  | .03 | Precast kerbing - SABS 927 figure 3:
|  |  | .01 | Radius up to 4 m | m | 44
|  |  | .02 | Radius over 4 m up to 20 m | m | 170
|  |  | .03 | Radius over 20 m and straight
|  |  |  | sections | m | 480
CB.03.04 |  | .04 | Precast kerbing - SABS 927 figure 7:
|  |  | .01 | Radius up to 4 m | m | 50
|  |  | .02 | Radius over 4 m up to 20 m | m | 110
|  |  | .03 | Radius over 20 m and straight
|  |  |  | sections | m | 500
CB.03.04 |  | .05 | Precast kerbing - C900:
|  |  | .01 | Radius up to 4 m | m | 94
|  |  | .02 | Radius over 4 m up to 20 m | m | 280
|  |  | .03 | Radius over 20 m and straight
|  |  |  | sections | m | 980
CA.05 |  | ERECTION AND REPAIR OF PERMANENT
ROAD TRAFFIC SIGNS
| 207 | Type R3 - Series 'R' 900mm no entry sign constructed of 1.4mm thick sheet steel in sign faces with galvanised background and symbols, characters, legends and borders in engineering grade retro-reflective material complete with reinforcement fitted on and including 125-150 mm diameter bitumen impregnated creosote pole bedded in and including unreinforced concrete base, including any necessary excavation, paint finish, stainless steel strapping, etc. |  |  | No | 2
| 208 | Type R1 - Series 'R' 900mm stop sign constructed of 1.4mm thick sheet steel in sign faces with galvanised background and symbols, characters, legends and borders in engineering grade retro-reflective material complete with reinforcement fitted on and including 125-150 mm diameter bitumen impregnated creosote pole bedded in and including unreinforced concrete base, including any necessary excavation, paint finish, stainless steel strapping, etc. |  |  | No | 2
Carried forward
Brought forward
CA.05.02 | 209 | Road sign supports (overhead road
sign structures excluded):
|  | .01 | Steel tubing (dia 76 mm and 3 mm
|  |  | wall thickness) |  | m | 8
CA.05.03 | 210 | Excavation and backfilling for road
sign supports (not applicable to
|  | kilometre posts) |  |  | m³ | 2
CA.05.04 | 211 | Extra over item CA 07.03 for cement-
|  | treated soil backfill |  |  | m³ | 2
CA.05.05 | 212 | Extra over item CA 07.03 for rock
|  | excavation |  |  | m³ | 1
CA.05.07 | 213 | Hazard plates (600 mm x 150 mm) |  |  | number | 6
CA.06 |  | ROAD MARKINGS
CA.06.01 | 214 | Prepare and apply one coat white reflective road marking paint on bituminous road surfacing, precast concrete paving blocks, concrete road surfacing, etc.:
|  | .01 | 100 mm wide broken or unbroken lines, white, yellow or red |  | m | 65
|  | .02 | 150 mm wide broken or unbroken lines, white, yellow or red |  | m | 65
|  | .03 | Straight directional arrow 300 x 3500mm overall. |  | number | 6
|  | .04 | Right/Left turn directional arrow 300 x 3500mm overall. |  | number | 4
|  | .05 | Straight directional arrow 500 x 3500mm overall with right/left turn side arrow 955 x 600mm overall. |  | number | 12
|  | .06 | Painted "STOP" sign with 2000mm high letters. |  | number | 4
CA.06.02 | 215 | Setting out and premarking of lines
(excluding traffic-island markings,
|  | lettering and symbols) |  |  | km | 2
SANS1200MJ | 216 | SEGMENTED PAVING
|  | .01 | Precast concrete paving blocks of
thickness 50 mm up to 75 mm:
|  |  | .01 | 450 mm x 450 mm | m² | 150
Carried forward
Brought forward
CA.01 |  | REPAIR OF GRAVEL WEARING COARSE
CA.01.01 | 217 | Reshaping the wearing course by:
|  | .01 | Grading only |  | m² | 4217
|  | .02 | Ripping, redistributing and compacting |  | m² | 4217
|  | .03 | Importing, placing and compacting |  | m³ | 1515.1
material from commercial sources (G5) in two 150mm layers
CA.01.01 | 218 | Construction of new earth side drains:
|  | .01 | Top width not exceeding 1,0 m and depth not exceeding 0,6 m |  | m | 390
|  | .02 | Top width not exceeding 2,0 m and depth not exceeding 0,6 m |  | m | 810
CA.01.02 | 219 | Overhaul on surplus material |  |  | m³-km | 1206
TEST BLOCKS
| 220 | Test blocks:
|  | .01 | Making and testing set of three 150 x 150 x 150mm concrete strength test cubes. |  | Sets | 52
| 221 | Finishing top surfaces of concrete with a power float to pan floated finish:
|  | .01 | Paving to parking areas, roads, etc to falls. |  | m² | 30
|  | .02 | Paving to parking areas, roads, etc. |  | m² | 40
|  | .03 | Paving to ramps, etc to falls. |  | m² | 20
REINFORCEMENT
CB.03.05 | 222 | Steel reinforcement |  |  | t | 0.4
| 223 | Fabric reinforcement:
|  | .01 | Mesh Ref 193 fabric reinforcement in concrete surface beds etc. |  | m² | 120
|  | .02 | Mesh Ref 243 fabric reinforcement in concrete surface beds etc. |  | m² | 90
|  | .03 | Mesh Ref 395 fabric reinforcement in concrete surface beds etc. |  | m² | 1350
Carried forward
Brought forward
CB.01 |  | PREFABRICATED CULVERT
INSTALLATION AND REPAIR OF
EXISTING CULVERTS AND
STRUCTURES
CB.01.01 | 224 | Excavation:
|  | .01 | Excavation of soft material within
the following depth ranges below
the surface level:
|  |  | .01 | 0 m up to and including 1,5 m | m³ | 27
CB.01.03 | 225 | Prefabricated culverts:
|  | .01 | On Class B bedding Class 100D pipe:
|  |  | .01 | 600 mm diameter | m | 40
CB.01.04 | 226 | Cast in situ concrete and formwork
in stormwater structures:
|  | .01 | Concrete
|  |  | .01 | Class 20 MPa concrete | m³ | 5
|  |  | .02 | Class 25 MPa concrete | m³ | 5
STORMWATER CHANNELS
| 227 | Precast or in-situ reinforced concrete (30Mpa) with mesh Ref 395, V- shaped stormwater channels, finished smooth on all exposed surfaces and with angles rounded, cast in suitable lengths (not exceeding 2 000mm), with bitumen applied to one edge at joints, and reinforced as necessary for handling if precast, including all formwork, reinforecing, moulds, shallow excavation, filling and ramming, laying to falls, bedding and pointing in (3:1) cement mortar:
CB.03.08 |  | .01 | 1500mm wide x 300mm V-Drain (125mm thick). |  | m | 700
CB.03.08 |  | .02 | 900mm wide x 300mm V-Drain (125mm thick). |  | m | 650
|  | .03 | D12 type open ended concrete channel |  | m | 1073
|  | .04 | Extra for angles, intersections, ends, dressing into sides of catchpits, etc. |  | No | 12
Carried forward
Brought forward
|  | .05 | 12mm Bitumen impregnated softboard, size 450mm wide x 150mm high with a V cut in the top to match the shape of the end of the channel, expansion joint between concrete stormwater channels. |  | m | 675
|  | .06 | 10 x 10mm 'Sikaflex Pro 3' Silicone sealing compound including backing cord, bond breaker, primer, etc, in isolation joint in channels including raking out expansion joint filler as necessary. |  | m | 675
STORMWATER DRAINAGE
CB.01.03 | 228 | Class 100D concrete pipes with interlocking joint pipes, including wrapping joints with 200mm wide strip of geotextile filter blanket with wrapping to overlap at least 200mm:
|  | .01 | 600mm Pipes laid in and including trenches not exceeding 1m deep. |  | m | 40
|  | .02 | 450mm Pipes laid in and including trenches not exceeding 1m deep. |  | m | 40
CB.01.01(a) | 229 | Extra over excavation in earth for pipe trenches, chambers, etc for excavation in soft rock. |  |  | m³ | 32
CB.01.01(b) | 230 | Extra over excavation in earth for pipe trenches, chambers, etc for excavation in hard rock. |  |  | m³ | 16
CB.01.02 | 231 | Extra over backfilling to pipe trenches, chambers, etc. for backfilling with soilcrete (10% cement) supplied by the Contractor |  |  | m³ | 16
CB.01.02 | 232 | Extra over backfilling to pipe trenches, chambers, etc. for backfilling with G7 material supplied by the Contractor to bedding and cradle in accordance with SABS 1200M compacted to 98 % Mod AASHTO density. |  |  | m³ | 32
CB.01.01(b) | 233 | Extra over excavation for pipe trenches, chambers, etc for carting away surplus material to a dumping site to be located by the Contractor. |  |  | m³ | 32
Carried forward
Brought forward
| 234 | Excavate for and build stormwater catch pit size 300 x 300 x exceeding 0,5m and not exceeding 1,0m deep internally, formed of 150mm thick cement concrete (25MPa) bottom projecting 75mm all round, mass concrete (15Mpa) benching, hard burnt one brick sides with galvanised brickforce between each course, rendered internally in 1:3 cement plaster, 760 x 760 x 200mm thick (25Mpa) reinforced concrete cover slab including reinforcing, rebating for and fitted with mild steel angle frame and grating (frame and grating elsewhere) in accordance with SABS 558, bedded in 1:3 cement mortar and sealed in tallow, including all necessary fittings, excavations, formwork, holes through sides for pipes. |  |  | number | 3
| 235 | Excavate for and build stormwater catch pit Type B size 600 x 600 x exceeding 0,5m and not exceeding 1,0m deep internally, formed of 150mm thick cement concrete (25MPa) bottom projecting 75mm all round, mass concrete (15Mpa) benching, hard burnt one brick sides with galvanised brickforce between each course, rendered internally in 1:3 cement plaster, 1800 x 1800 x 200mm thick (25Mpa) reinforced concrete cover slab including reinforcing, rebating for and fitted with mild steel angle frame and grating (frame and grating elsewhere) in accordance with SABS 558, bedded in 1:3 cement mortar and sealed in tallow, including all necessary fittings, excavations, formwork, holes through sides for pipes etc. |  |  | number | 3
| 236 | Excavate for and build stormwater catch pit Type A size 650 x 900 x exceeding 1,5m and not exceeding 2,0m deep internally, formed of 150mm thick cement concrete (25MPa) bottom projecting 75mm all round, mass concrete (15Mpa) benching, hard burnt one brick sides with galvanised brickforce between each course, rendered internally in 1:3 cement plaster, 2400 x 880mm overall x 200mm thick (25Mpa) reinforced concrete cover slab including reinforcing, rebating for and fitted with mild steel angle frame and grating (frame and grating elsewhere) in accordance with SABS 558, bedded in 1:3 cement mortar and sealed in tallow, including all necessary fittings, excavations, formwork, holes through sides for pipes etc. |  |  | number | 1
Carried forward
Brought forward
| 237 | PITCHING, STONEWORK AND PROTECTION AGAINST EROSION
|  | .01 | Stone Pitching
|  |  | .01 | Grouted stone pitching | m² | 150
|  |  | .02 | Grouted stone pitching on a concrete bed max 150mm thick | m² | 55
GRATINGS, COVERS, ETC:
| 238 | 600 x 600mm Hot dipped galvanised angle section frame and grating, comprising of 70 x 70 x 8mm angle iron frame size 630 x 630mm cast into concrete and grating size 600 x 600mm comprising of 60 x 8mm flat iron support frame filled in with 50mm diameter high tensile steel bars at 100mm centres installed complete as detailed on Stormwater Cachpit. |  |  | number | 3
| 239 | 900 x 650mm Hot dipped galvanised angle section frame and grating, comprising of 50 x 50 x 6mm angle iron frame size 930 x 680mm cast into concrete and grating size 900 x 650mm comprising of 40 x 6mm flat iron support frame filled in with 25mm diameter high tensile steel bars at 65mm centres installed complete as detailed on Stormwater Cachpit |  |  | number | 3
CB.02 |  | CLEANING OF PREFABRICATED
CULVERTS
| 240 | Cleaning of prefabricated culverts
and inlet structures
CB.04.01 |  | .01 | Prefabricated concrete pipes and
portal culverts
|  |  | .01 | Up to and including 500 mm | m | 48
|  |  | .02 | Over 500 mm up to 750 mm | m | 24
CB.02.02 |  | .02 | Clean grid inlets |  | number | 8
TOTAL SCHEDULE NO 2 CARRIED TO SUMMARY

## CALCULATION TENDER SUM
SOUTH AFRICAN NATIONAL BIODIVERSITY INSTITUTE
KAROO DESERT NATIONAL BOTANICAL GARDENS: RING ROAD UPGRADE, GRAVEL SERVICE ROAD UPGRADE AND STROMWATER MANAGEMENT
CALCULATION OF TENDER SUM
TOTAL OF SCHEDULE NO 1: GENERAL . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . | R | ….............................
TOTAL OF SCHEDULE NO 2: ROADS AND STORMWATER DRAINAGE . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . | R | ….............................
SUBTOTAL . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . | R | ….............................
VALUE-ADDED TAX (VAT)
The tenderer shall add 15% of the subtotal for value-added tax . . . . . . . . . . . . . . . . . . . . . . . . . | R | ….............................
TENDER SUM CARRIED TO FORM OF TENDER | R | ….............................
SIGNED ON BEHALF OF TENDERER : . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .