## Ps & Gs
CONTRACT NUMBER: |  | STRUCTURAL TIMBER REFURBISHMENT STONE COTTAGES AT KIRSTENBOSCH NBG CAPE TOWN |  |  |  | SECTION 1
ITEM | PAYMENT | DESCRIPTION |  |  | RATE
NO | REFERS |  | UNIT | QUANTITY |  | AMOUNT
TO
1 | SABS | PRELIMINARY AND GENERAL
1200 A
1.1 | 8.3 | SCHEDULED FIXED-CHARGE AND VALUE-RELATED
ITEMS
1.1.1 | 8.3.1 | Contractural Requirements | Sum | 1
1.1.2 | 8.3.3 | Other fixed-charge obligations | Sum | 1
(including all health and safety requirements)
1.2 | 8.4 | SCHEDULED TIME-RELATED ITEMS
1.2.1 | 8.4.1 | Contractural requirements | Sum | 1
1.2.2 | 8.4.3 | Supervision for duration of construction | Prov. Sum | 1
1.2.3 | 8.4.4 | Company and head office overhead costs for the | Sum | 1
duration of the contract
1.2.4 | 8.4.5 | Other Time-related obligations | Sum | 1
(including all health and safety requirements)
1 - Ps & Gs
TOTAL SECTION 1 PRELIMINARY AND GENERAL CARRIED TO SUMMARY

## Structural Timber Refurbishment
CONTRACT NUMBER: |  | STRUCTURAL TIMBER REFURBISHMENT STONE COTTAGES AT KIRSTENBOSCH NBG CAPE TOWN | [5 empty] | SECTION 2
ITEM | PAYMENT | DESCRIPTION |  |  |  |  | RATE
NO | REFERS |  |  |  | UNIT | QUANTITY |  | AMOUNT
TO
2 |  | STRUCTURAL TIMBER
|  |  | (i) | All timber to be treated and all elements
should match existing sizes or as per
drawing 2110-S-01
|  |  | (ii) | All structural timber properties to be submitted
to engineer for approval before fabrication and
installation
2.1 |  | SCHEDULED ITEMS
2.1.1 |  | Preparation of shop drawings (Timber beams, |  |  | Sum | 1
columns and brace for the three stone cottages from
site measurements by contractor)
2.1.2 |  | Propping and removal of damaged beams, columns
and brace (Use lime as cement replacement in all
concrete and masonry works)
|  | (i) | Front Patio roof propping |  | No. | 3
|  | (ii) | Removal of beams, column & bracing at each |  | No. | 2
patio
|  | (iii) | Removal of beam over patio |  | No. | 1
2.1.3 |  | Installation of solid wood beams, brace and columns
at patio
|  | (i) | Beams, column & bracing at patio of cottage |  | No. | 2
1 & 2 (see drawing 2110-S-01)
|  | (ii) | Beam at over cottage 3 patio (see drawing |  | No. | 1
2110-S-01)
2.1.4 |  | Replace and make good all deteriorated or |  |  | Sum | 1
construction damaged patio ceiling for the three
cottage (Total ceiling area 36,0m2)
2.1.5 |  | Painting
|  | (i) | Apply prime coat all all new instalations |  | Sum | 1
|  | (ii) | Apply two coats of enamel paint to all new |  | Sum | 1
instsllstions to match the existing for all
refurbished structural timber elements
and ceiling
2.1.6 |  | Cleaning up and making good |  |  | Sum | 1
2-Struc - Timber
TOTAL SECTION 2 - STRUCTURAL TIMBER CARRIED TO SUMMARY

## SUMMARY
CONTRACT NUMBER: |  | STRUCTURAL TIMBER REFURBISHMENT STONE COTTAGES AT KIRSTENBOSCH NBG CAPE TOWN | SUMMARY
DESCRIPTION
AMOUNT
SECTION | 1 | PRELIMINARY AND GENERAL
SECTION | 2 | STRUCTURAL TIMBER
SUBTOTAL
ADD 5% CONTIGENCY
TOTAL
ADD 15% VAT
TOTAL PROJECT CONSTRUCTION COSTS