## Bill 1
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  |  | Bill
Q9308 | [6 empty] | 1
Item | DESCRIPTION |  |  |  |  | RATE
No. |  |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 1
PRELIMINARIES AND GENERAL
MEANING OF TERMS "TENDER / TENDERER"
Any reference to the words "Tender" or "Tenderer" herein and/or
in any other documentation shall be construed to have the same
meaning as the words "Bid" or "Bidder"
PRELIMINARIES
The JBCC Preliminaries, May 2018 edition for use with the JBCC
Principal Building Agreement Edition 6.2 is taken to be incorporated
herein. The tenderer is deemed to have referred to these
documents for the full intent and meaning of each clause. These
clauses are referred to by number and heading only. Where
standard clauses or options are not applicable to the contract such
modifications or corrections as are necessary are given under each
relevant clause. Where an item is not relevant to this specific
contract such item is marked "N/A" signifying "Not Applicable"
PRICING OF PRELIMINARIES
Should Option A, as set out in clause B10.3.1 hereinafter be used
for the adjustment of preliminaries then each item priced is to be
allocated to one or more of the three categories Fixed, Value
Related or Time Related the spaces provided under each item
Items not priced in these Preliminaries shall be deemed to be
included elsewhere in these Bills of Quantities
SECTION A: JBCC PRINCIPAL BUILDING AGREEMENT
DEFINITIONS AND INTERPRETATION
1 | A1.0 | DEFINITIONS AND INTERPRETATION
Clause 1.0
| Clause 1.1 |  | Definition of "Corrupt Practice" is added:
"CORRUPT PRACTICE" means the offering, giving, receiving or
soliciting of anything of value to influence the action of a public
official in the procurement process or in contract execution
Clause 1.1 Definition of "Fraudulent Practice" is added:
"FRAUDULENT PRACTICE" means a misrepresentation of facts in
order to influence a procurement process or the execution of a
contract to the detriment of any tenderer and includes collusive
practice among tenderers (prior to or after the tender submission)
designed to establish tender prices at artificial non- competitive
levels and to deprive the tenderer of the benefits of free and open
competition
| Clause 1.1 |  | Definition of "Interest" is amended by replacing it with
"INTEREST" means the interest rates applicable on this contract,
whether specifically indicated in the relevant clauses or not, will be
the rate as determined by the Minister of Finance, from time to
time, in terms of section 80(1)(b) of the Public Finance Management
Act, 1999 (Act No. 1 of 1999)
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  |  | Bill
Q9308 | [6 empty] | 1
ITEM | PAYMENT | DESCRIPTION |  |  |  | RATE
NO | REFERS |  |  | UNIT | QUANTITY |  | AMOUNT
TO
| Clause 1.1 |  | Definition of "Principal Agent" is amended by
replacing it with the following:
"PRINCIPAL AGENT" means the person or entity appointed by the
employer and named in the schedule. In the event of a principal
agent not being appointed, then all the duties and obligations of a
principal agent as detailed in the agreement shall be fulfilled by
a representative of the employer as named in the schedule
| Clause 1.1 |  | Definition of "Security" is amended by replacing it with
the following:
"SECURITY" means the form of security provided by the employer
or contractor, as stated in the schedule, from which the contractor
or employer may recover expense or loss
2 | A10.0 |  | INSURANCES
Clause 10.0
| Clause 10.0 |  | is amended by the addition of the following clauses:
| 10.11 |  | Damage to the Works
| (a) |  | Without in any way limiting the contractor's obligations
in terms of the contract, the contractor shall bear the
full risk of damage to and/or destruction of the works
by whatever cause during during construction of the
works and hereby indemnifies and holds harmless the
employer against any such damage. Thecontractor
shall take such precautions and security measures and
other steps for the protection and security of the works
as the contractor may deem necessary
| (b) |  | The contractor shall at all times proceed immediately
to remove or dispose of any debris arising from damage
to or destruction of the works and to rebuild, restore,
replace and/or repair the works
| (c) |  | The employer shall carry the risk of damage to or destruction of
the works and materials paid for by the employer that
is the result of the excepted risks as set out in 10.12
| (d) |  | Where the employer bears the risk in terms of this
contract, the contractor shall, if requested to do so,
reinstate any damage or destroyed portions of the
works and the costs of such reinstatement shall be
measured and valued in terms of 27.0 hereof
| 10.12 |  | Injury to Persons or loss of or damage to
Properties
| (a) |  | The contractor shall be liable for and hereby
indemnifies the employer against any liability, loss,
claim or proceeding whether arising in common law or
by statute, consequent upon personal injuries to or the
death of any person whomsoever arising out of or in
the course of or caused by the execution of the works
unless due to any act or negligence of any person for
whose actions the employer is legally liable
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  |  | Bill
Q9308 | [6 empty] | 1
ITEM | PAYMENT | DESCRIPTION |  |  |  | RATE
NO | REFERS |  |  | UNIT | QUANTITY |  | AMOUNT
TO
| (b) |  | The contractor shall be liable for and hereby
indemnifies the employer against any liability, loss,
claim or proceeding consequent upon loss of or
damage to any moveable or immovable or personal
property or property contiguous to the site, whether
belonging to or under the control of the employer or
any other body or person, arising out of or in the
course of or by reason of the execution of the works
unless due to any act or negligence of any person for
whose actions the employer is legally liable
| (c) |  | The contractor shall, upon receiving a contract
instruction from the principal agent, cause the same to
be made good in a perfect and workmanlike manner at
his own cost and in default thereof the employer shall
be entitled to cause it to be made good and to recover
he cost thereof from the contractor or to deduct the
same from amounts due to the contractor
| (d) |  | The contractor shall be responsible for the protection
and safety of such portions of the premises placed
under his control by the employer for the purpose of
executing the works until the issue of the certificate of
practical completion
| (e) |  | Where the execution of the works involves the risk of
removal of or interference with support to adjoining
properties including land or structures or any structures
to be altered or added to, the contractor shall obtain
adequate insurance and will remain adequately insured
or insured to the specific limit stated in the contract
against the death of or injury to persons or damage to
such property consequent on such removal or
interference with the support until such portion of the
works has been completed
| (f) |  | The contractor shall at all times proceed immediately
at his own cost to remove or dispose of any debris and
to rebuild, restore, replace and/or repair such property
and to execute the works
| 10.13 |  | High risk insurance
In the event of the project being executed in a geological
area classified as a "High Risk Area", that is an area which
is subject tohighly unstable subsurface conditions that
might result in catastrophic ground movement evident by
sinkhole or doline formation the following will apply:
| 10.13.1 |  | Damage to the works
The contractor shall, from the commencement date of the
works until the date of the certificate of practical completion
bear the full risk of and hereby indemnifies and holds
harmless the employer against any damage to and/or
destruction of the works consequent upon a catastrophic
ground movement as mentioned above. The contractor
shall take such precautions and security measures and
other steps for the protection of the works as he may deem
necessary
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  |  | Bill
Q9308 | [6 empty] | 1
ITEM | PAYMENT
NO | REFERS | [5 empty] | AMOUNT
TO
When so instructed to do so by the principal agent, the
contractor shall proceed immediately to remove and/or
dispose of any debris arising from damage to or destruction
of the works and to rebuild, restore, replace and/or repair
the works, at the contractor's own costs
| 10.13.2 |  | Injury to persons or loss of or damage to property
The contractor shall be liable for and hereby indemnifies
and holds harmless the employer against any liability, loss,
claim or proceeding arising at any time during the period of
the contract whether arising in common law or by statute,
consequent upon personal injuries to or the death of any
person whomsoever resulting from, arising out of, or
caused by a catastrophic ground movement as mentioned
above
The contractor shall be liable for and hereby indemnifies
the employer against any and all liability, loss, claim or
proceeding consequent upon loss of or damage to any
moveable or immovable or personal property or property
contiguous to the site, whether belonging to or under the
control of the employer or any other body or person
whomsoever arising out of or caused by a catastrophic
ground movement, as mentioned above, which occurred
during the period of the contract
| 10.13.3 | It is the responsibility of the contractor to ensure that he
has adequate insurance to cover his risk and liability as
mentioned in 10.7.1 and 10.7.2. Without limiting the
contractor's obligations in terms of the contract, the
contractor shall, within twenty-one (21) calendar days of the
commencement date but before commencement of the
works, submit to the employer proof of such insurance
policy, if requested to do so
3 | A11.0 |  | SECURITIES
Clause 11.0
Clauses 11.1 - 11.10 are amended by replacing them with the
following
| 11.1 | In respect of contracts with a contract sum up to R1 million,
the security to be provided by the contractor to the
employer will be a payment reduction of five per cent (5%)
of the value certified in the payment certificate
(excluding VAT)
| 11.1.1 | The payment reduction of the value certified in a payment
certificate shall be mutatis mutandi in terms
| 11.1.2 | The employer shall be entitled to recover expense and loss
from the payment reduction in terms of 27.0 provided that
the employer complies with the provisions of 27.4 in which
event the employer's entitlement shall take precedence
over his obligations to refund the payment reduction
security or portions thereof to the contractor
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  |  | Bill
Q9308 | [6 empty] | 1
Item | DESCRIPTION |  |  |  |  | RATE
No. |  |  |  | UNIT | QUANTITY |  | AMOUNT
| 11.2 | In respect of contracts with a contract sum above
R1 million, the contractor shall have the right to select the
security to be provided in terms of 11.3, 11.4, 11.5, 14.6,
or 11.7 as stated in the schedule. Such security shall be
provided to the employer within twenty-one (21) calendar
days from commencement date. Should the contractor
fail to select the security to be provided or should the
contractor fail toprovide the employer with the selected
security within twenty-one (21) calendar days from
commencement date, the security in terms of 11.7
shall be deemed to have been selected
| 11.3 | Where security as a cash deposit of ten per cent (10%) of
the contract sum (excluding VAT) has been selected:
| 11.3.1 | The contractor shall furnish the employer with a cash
deposit equal in value to ten per cent (10%) of the contract
sum (excluding VAT) within twenty- one (21) calendar
days from commencement date
| 11.3.2 | Within twenty-one (21) calendar days of the date of
practical completion of the works the employer shall
reduce the cash deposit to an amount equal to three
percent (3%) of the contract value (excluding VAT), and
refund the balance to the contractor
| 11.3.3 | Within twenty-one (21) calendar days of the date of final
completion of the works the employer shall reduce the
cash deposit to an amount equal to one per cent (1%) of
the contract value (excluding VAT) and refund the
balance to the contractor
| 11.3.4 | On the date of payment of the amount in the final payment
certificate, the employer shall refund the remainder of
the cash deposit to the contractor
| 11.3.5 | The employer shall be entitled to recover expense and loss
from the cash deposit in terms of 33.0 provided that the
employer complies with the provisions of 33.4 in which
event the employer's entitlement shall take precedence
over his obligations to refund the cash deposit security or
portions thereof to the contractor
| 11.3.6 | The parties expressly agree that neither the employer nor
the contractor shall be entitled to cede the rights to the
deposit to any third party
| 11.4 | Where security as a variable construction guarantee of
ten percent (10%) of the contract sum (excluding VAT) has
been selected:
| 11.4.1 | The contractor shall furnish the employer with an
acceptable variable construction guarantee equal in
value to ten per cent (10%) of the contract sum
(excluding VAT) within twenty-one (21) calendar days from
commencement date
Clause 11.4.1 is deemed to be amended by the addition of the
following sentence;
No interest will be paid on such amounts withheld
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  |  | Bill
Q9308 | [6 empty] | 1
ITEM | PAYMENT | DESCRIPTION |  |  |  | RATE
NO | REFERS |  |  | UNIT | QUANTITY |  | AMOUNT
TO
| 11.4.2 | The variable construction guarantee shall reduce and
expire in terms of the Variable Construction Guarantee
form included in the invitation to tender
| 11.4.3 | The employer shall return the variable construction
guarantee to the contractor within fourteen (14) calendar
days of it expiring
| 11.4.4 | Where the employer has a right of recovery against the
contractor in terms of 33.0, the employer shall issue a
written demand in terms of the variable construction
guarantee
| 11.5 | Where security as a fixed construction guarantee of five
percent (5%) of the contract sum (excluding VAT) and a
five per cent (5%) payment reduction of the value certified
in the payment certificate (excluding VAT) has been
selected:
| 11.5.1 | The contractor shall furnish a fixed construction
guarantee to the employer equal in value to five per cent
(5%) of the contract sum (excluding VAT)
| 11.5.2 | The fixed construction guarantee shall come into force on
the date of issue and shall expire on the date of the last
certificate of practical completion
| 11.5.3 | The employer shall return the fixed construction
guarantee to the contractor within fourteen (14)
calendar days of it expiring
| 11.5.4 | The payment reduction of the value certified in a payment
certificate shall be in terms of clause 25.
| 11.5.5 | Where the employer has a right of recovery against the
contractor in terms of 27.0, the employer shall be entitled
to issue a written demand in terms of the fixed
construction guarantee or may recover from the
payment reduction or may do both
| 11.6 | Where security as a cash deposit of five per cent (5%) of
the contract sum (excluding VAT) and a payment
reduction of five per cent (5%) of the value certified in the
payment certificate (excluding VAT) has been selected:
| 11.6.1 | The contractor shall furnish the employer with a cash
deposit equal in value to five per cent (5%) of the contract
sum (excluding VAT) within twenty- one (21) calendar days
from commencement date
| 11.6.2 | Within twenty-one (21) calendar days of the date of
practical completion of the works the employer shall
refund the cash deposit in total to the contractor
| 11.6.3 | The payment reduction of the value certified in a payment
certificate shall be mutatis mutandi in terms of 25
| 11.6.4 | Where the employer has a right of recovery against the
contractor in terms of 27.0, the employer may issue a
written notice in terms of 27.4 or may recover from the
payment reduction or may do both
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  |  | Bill
Q9308 | [6 empty] | 1
ITEM | PAYMENT | DESCRIPTION |  |  |  | RATE
NO | REFERS |  |  | UNIT | QUANTITY |  | AMOUNT
TO
| 11.7 | Where security as a payment reduction of ten percent
(10%) of the value certified in the payment certificate
(excluding VAT) has been selected:
| 11.7.1 | The payment reduction of the value certified in a payment
certificate shall be mutatis mutandi in terms of 25
| 11.7.2 | The employer shall be entitled to recover expense and
loss from the payment reduction in terms of 27.0 provided
that the employer complies with the provisions of 27.4 in
which event the employer's entitlement shall take
precedence over his obligations to refund the payment
reduction or portions thereof to the contractor
| 11.8 | Payments made by the guarantor to the employer in terms
of the fixed or variable construction guarantee shall not
prejudice the rights of the employer or contractor in terms
of this agreement
EXECUTION
4 | A12.0 OBLIGATIONS OF THE PARTIES
Clause 12.0
Clause 12.1.1 is amended by replacing it with:
No clause
Clause 12.2.4 is amended by the addition of the following clause:
| 12.2.4 | An acceptable health and safety plan, required in terms of
the Occupational Health and Safety Act, 1993
(Act 85 of 1993), within twenty-one (10) calendar days of
commencement date
PAYMENT
5 | A25.0 PAYMENT
Clause 25.0
Notwithstanding this or any other clause, materials and goods stored
off site shall not be included in the amount authorized for payment.
The first sentence of sub-clause 25.10 is deemed to be deleted and
replaced with the following:
The employer shall pay the contractor the amount certified within
thirty (30) calendar days of the date.
Fixed:_________Value related:_________Time related:__________
SUSPENSION AND TERMINATION
6 | A28.0 SUSPENSION BY CONTRACTOR
Clause 28.0
Fixed:_________Value related:_________Time related:__________
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  |  | Bill
Q9308 | [6 empty] | 1
ITEM | PAYMENT
NO | REFERS | [5 empty] | AMOUNT
TO
7 | A29.0 TERMINATION
Clause 29.0
Add the following sub-clauses 29.1.4 to 29.1.6 under 29.1 to read as
follows:
| 29.1.4 | The contractor’s refusal or neglect to comply strictly with
any of the conditions of contract.
| 29.1.5 | The contractor’s estate being sequestrated, liquidated or
surrendered in terms of the insolvency laws in force with
the Republic of South Africa.
| 29.1.6 | The contractor, in the judgment of the employer, has
engaged in corrupt or fraudulent practices in competing for
or in executing the contract.
Replace clause 29.3 with the following:
the employer may give notice of cancellation should the
contractor remain in default for ten (10) working days after
the date of of issue of such a notice of default
Clause 29.25.4
Replace “Sixty (60)” with “one hundred and twenty (120)”.
Add the following sub-clauses 29.29 under 29 to read as
follows: Notwithstanding any clause to the contrary, on
cancellation of this agreement either by the employer or the
contractor, or for any reason whatsoever, the contractor
shall on written instruction, discontinue with the works on a
stated date and withdraw himself from the site. The
contractor shall not be entitled to refuse to withdraw from
the works on the grounds of any lien or right of retention or
on the grounds of any other right whatsoever.
Fixed:_________Value related:_________Time related:__________
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  |  | Bill
Q9308 | [6 empty] | 1
ITEM | PAYMENT
NO | REFERS | [5 empty] | AMOUNT
TO
SECTION B: JBCC PRELIMINARIES
This schedule contains all variables referred to in this document and
is divided into pre-tender and post-tender categories. The
pre-tender category must be completed in full and included in the
tender documents. Both the pre-tender and post-tender categories
form part of these Preliminaries
Spaces requiring information must be filled in, shown as
"not applicable" or deleted and not left blank. Where choices are
offered, the non-applicable items are to be deleted. Where
insufficient space is provided the information should be annexed
hereto and cross-referenced to the applicable clause of the
schedule. Key cross reference clauses are italicised in [ ] brackets
| 12.1 | PRE-TENDER INFORMATION
| 12.1.1 | Provisional bills of quantities
| [2.2] | The quantities are provisional
YES/NO
| 12.1.2 | Availability of construction documentation
| [2.3] | Construction documentation is complete
YES/NO
| 12.1.3 | Interests of agents
| [2.4] | Details:
| 12.1.4 | Defined works area
| [3.1] | Details:
| 12.1.5 | Geotechnical investigation
| [3.2] | Details:
| 12.1.6 | Existing premises occupied
| [3.4] | Details:
| 12.1.7 | Previous work - dimensional accuracy
| [3.5] | Details:
| 12.1.8 | Previous work - defects
| [3.6] | Details:
| 12.1.9 | Services - known
| [3.7] | Details:
| 12.1.10 | Protection of trees
| [3.9] | Details:
| 12.1.11 | Inspection of adjoining properties
| [3.11] | Details:
| 12.1.12 | Enclosure of the works
| [6.2] | Details:
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  |  | Bill
Q9308 | [6 empty] | 1
ITEM | PAYMENT
NO | REFERS | [5 empty] | AMOUNT
TO
| 12.1.13 | Offices
| [6.4.3] | Specific requirements:
The contractor shall provide, maintain and remove on
completion of the works an office for the exclusive use of
the principal agent, minimum size 4 x 3 x 3m high internally,
suitably insulated and ventilated, provided with electric
lighting and fitted with boarded floor, desk, chair, drawing
stool, drawing board and lock-up drawers for drawings. The
office shall be kept clean and fit for use at all times
| 12.1.14 | Main notice board
| [6.5] | Specific requirements:
The contractor shall provide, erect where directed, maintain
and remove on completion of the works a notice board size
3 x 3m as per Drawing, constructed of suitable boarding
with flat smooth surface and with edging bead 19mm thick
round outer edges and projecting 12mm from face of
boarding and rounded on front edge. The board shall be
securely fixed to hoarding, where hoarding is provided, or
fixed to and including a suitable supporting structure of
timber or tubular posts and braces. The board is to be
painted ivory white and the bead and 12mm wide dividing
lines dark green. All wording shall be inscribed in dark
green as per the coat of arms for SA. All wording shall be
inscribed in dark green painted sans serif lettering
| 12.1.15 | Subcontractors' notice board
| [7.2] | A notice board is required
YES/NO
Specific requirements:
| 12.1.16 | Water
| [7,3] | Option A (by contractor)
YES/NO
Option B (by employer - free of charge)
YES/NO
Option C (by employer - metered)
YES/NO
| 12.1.17 | Electricity
| [6.6] | Option A (by contractor)
YES/NO
Option B (by employer - free of charge)
YES/NO
Option C (by employer - metered)
YES/NO
| 12.1.18 | Telecommunications
| [7.4] | Option A (by contractor)
YES/NO
Option B (by employer - free of charge)
YES/NO
Option C (by employer - metered)
YES/NO
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  |  | Bill
Q9308 | [6 empty] | 1
ITEM | PAYMENT
NO | REFERS | [5 empty] | AMOUNT
TO
| 12.1.19 | Ablution facilities
| [7.5] | Option A (by contractor)
YES/NO
Option B (by employer)
YES/NO
| 12.1.20 | Protection of existing/sectionally occupied works
| [11.2] | Option A (by contractor)
YES/NO
| 12.1.21 | Special attendance
| [9.2] | Subcontractor (1) details:
Subcontractor (2) details:
Subcontractor (3) details:
Subcontractor (4) details:
| 12.1.22 | Special attendance
| [11.1] | Specific requirements:
| 12.1.23 | Disturbance
| [11.1] | Specific requirements:
The contractor shall keep the site, structures, etc
well-watered during operations to prevent dust and shall
provide and erect and remove on completion of the works
all necessary temporary dust screens all to the satisfaction
of the principal agent
| 12.1.24 | Environmental disturbance
| [11.6] | Specific requirements:
| 12.2 | POST-TENDER INFORMATION
| 12.1.19 | Payment of preliminaries
| [7.5] | Option A (prorated)
YES/NO
Option B (calculated)
YES/NO
| 12.2.2 | Adjustment of preliminaries
| [10.3] | Option A (prorated)
YES/NO
Option B (calculated)
YES/NO
| 12.2.3 | Additional agreed preliminaries items
Details:
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  |  | Bill
Q9308 | [6 empty] | 1
ITEM | PAYMENT
NO | REFERS | [5 empty] | AMOUNT
TO
SECTION C: SPECIFIC PRELIMINARIES
Section C contains specific preliminary items which apply to this
contract except where N/A (Not Applicable) appears against an item
8 | C10.0 | HIV/AIDS AWARENESS
It is required of the contractor to thoroughly study the HIV/AIDS
Specification (PW 1544) of the Department that must be read
together with and is deemed to be incorporated under this Section
of the bills of quantities / lump sum document. Provision for
pricing of HIV/AIDS awareness is made under items C10.1 to C10.5
hereafter and it is explicitly pointed out that all requirements of the
aforementioned specification are deemed to be priced hereunder,
as the said items represent the only method of measurement and no
additional items or extras to the contract in this regard shall be
entertained
The contractor must take note that compliance with the HIV/AIDS
Specification is compulsory. In the event of partial or total
non-compliance, the principal agent, notwithstanding the provisions
of clause A 31.0 of Section A or any other clause to the contrary,
reserves the right to delay issuing any progress payment certificate
until the contractor provides satisfactory proof of compliance. The
contractor shall not be entitled to any compensation of whatsoever
nature, including interest, due to such delay of payment
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  |  | Bill
Q9308 | [6 empty] | 1
ITEM | PAYMENT |  |  | Page No.
NO | REFERS | [5 empty] | AMOUNT
TO
ALTERATIONS
COLLECTION
| Total Brought Forward from Page No. |  |  | 1
2
3
4
5
6
7
8
9
10
11
12
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to Summary

## Bill 2
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 2
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 2
ALTERATIONS TO EXISTING BUILDING
| Notes: 1. | Tenderers are advised to study the 'Construction
specification PW371-A and B as amended (downloadable
from Department of Public Works website,
www.publicworks.gov.za) beforepricing this bill 2. Unless
otherwise stated all items in this Bill
GENERAL NOTES
For further preambles and full descriptions of items not fully
described in this Bill, reference must be made to supplementary
preambles and descriptions in the other Bills of this Section. Such
supplementary preambles and descriptions shall apply equally
GENERAL
In taking down and removing existing work the utmost care
shall be observed to prevent any structural or other damage
building to remaining portions of the and the Contractor shall
provide all shoring, needling, strutting, etc. to ensure stability
Any water supply and other piping that may be encountered
and which is found necessary to disconnect or cut shall,
after such disconnection or cutting has been authorised by
the Representative/Agent, be effectively stopped off
EXISTING BUILDINGS
The existing buildings will be in use and occupied during the
progress of the contract and the Contractor will be required to carry
out the works insuch a manner as will least interfere with the
occupants and with the minimum of disturbance
SIZE PERTAINING TO EXISTING WORK
The Contractor is advised to take all dimensions affecting
the existing buildings on the site and he will be held solely
responsible for the correctness of sizes of all new work. All
sizes given in relation to existing work are approximate.
MAKING GOOD DAMAGED WORK
The Contractor shall make good in all trades to existing work
where damaged or disturbed through the alterations with all
necessary new materials to match the existing
FORMING NEW OPENINGS OR ALTERING OPENINGS IN
EXISTING WALLS
Descriptions of forming new openings or altering openings in
existing walls shall be deemed to include breaking out for and
forming new brick, in- situ concrete or prestressed concrete lintels,
including all reinforcement, formwork,
BUILDING UP OPENINGS
Descriptions of building up existing openings were given in
number shall be deemed to include preparing existing
surfaces all around, brickwork properly toothed and bonded
to existing, wedging up and making good on both sides as
described
BILL No. 2
Bill No. 2 Alterations carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 2
ITEM | PAYMENT | DESCRIPTION |  |  | RATE
NO | REFERS |  | UNIT | QUANTITY |  | AMOUNT
TO
PAINTWORK
Where plasterwork on walls, ceilings, etc. are required to be
patched or made good, prices are to include for the
appropriate priming coat and oneundercoat to receive paint
finishing coats which are measured elsewhere
The contractor must protect all work not removed such as
walls, floors, doors, windows, fittings, etc. from damage
during the progress of the work and provide all necessary
materials for doing so.
Tenderers are advised to visit the site before tendering and satisfy
themselves as to the nature and extent of the works, means of
access to the site and availability of working space. No claims will
be entertained due to the tenderer having failed to com
PROCEDURE OF WORK
The Representative/Agent reserves the right to direct the order in
which the contract will be executed, should circumstances
necessitate such action.
LOSS BY THEFT, FIRE OR OTHERWISE
The risk of loss, theft, fire, storm, riot or otherwise of the
buildings to be demolished and the materials therein shall
rest entirely with the contractor immediately upon the
handing over of the site.
WATER AND OTHER PIPING
Any water supply or other piping that may be met with and found
necessary to disconnect or cut are to be effectually stopped off or
grubbed up and removed and any new connections that may be
necessaryand are to be made with proper fittings
ELECTRICAL AND OTHER SERVICES
Special care is to be exercised not to unnecessarily interfere with
any electric light, bell, power, telephone or other wires and fittings
that may be met with and due notice must be given to the Architect.
The contractor must protect all work not removed such as walls,
floors, doors, windows, fittings, etc. from damage during the
progress of the work and all necessary materials for doing so
OCCUPATION OF EXISTING BUILDINGS
Tenderers are advised that the existing buildings will be in
occupation during the building operations and due allowance must
be made for the work being carried out in such a manner as will
least interfere with the general routine of the occupants
ALTERATIONS TO OPENINGS
Where the Contractor is required to form openings, alter
openings or brickup openings in existing walls all brickwork
shall be made good at jambs including properly bonding to
existing. Brickwork in bricking up openings shall be
wedged and pinned up to
BILL No. 2
Bill No. 2 Alterations carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 2
ITEM | PAYMENT | DESCRIPTION |  |  | RATE
NO | REFERS |  | UNIT | QUANTITY |  | AMOUNT
TO
OCCUPATION OF EXISTING BUILDINGS
Tenderers are advised that the existing buildings will be in
occupation during the building operations and due
allowance must be made for the work being carried out in
such a manner as will least interfere with the general
routine of the occupants
NOISE PREVENTION
The contractor shall take special care to minimise noisy
operations during business hours. Such measures will
include, inter alia, the use of silent compressors and strict
control of workmen
The contractor shall demolish the portions of existing
structures or buildings with a minimum amount of damage to
adjoining buildings, materials, paving, etc. Any damage
caused is to be made good at his own expense with
materials to match the existing.
MAKING GOOD, ETC
Prices are to include for making good in all trades to
existing work, where damaged or disturbed through
alterations, with all necessary new materials to match
existing and leave complete and perfect in every respect.
TEMPORARY BARRIERS, SCREENS, ETC
Temporary barriers, screens, etc including removal
1 | Allowance for all necessary temporary tarpaulins, barricades, |  | Item
screens, fencing, temporary waterproofing, dust proofing, etc
required to isolate buildings, walkways, pavements or any sections
under construction including any sections of new or existing
buildings for the purposes of excluding users from the remainder of
the building
REMOVAL OF EXISTING WORK
Taking out and removing doors, windows, etc, including
thresholds, sills, etc (building up openings and making
good finishes elsewhere)
Windows, doors, shopfront, etc
3 | Shopfront |  | m2 | 250
Taking down and removing roofs, floors, panelling,
ceilings, partitions, etc
Roofs
4 | Concrete roofing tiles |  | m2 | 660
Removing waterproofing, etc from concrete or brickwork
and preparing surfaces for new screeds, plaster, tile
finishes, waterproofing etc
5 | Water proofing |  | m2 | 136
BILL No. 2
Bill No. 2 Alterations carried to collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 2
ITEM | PAYMENT |  | Page No.
NO | REFERS |  |  |  |  | AMOUNT
TO
ALTERATIONS
COLLECTION
| Total Brought Forward from Page No. |  | 1
2
3
BILL No. 2
Bill No. 2 Alterations carried to Summary

## Bill 3
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 3
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 3
EARTHWORKS
Tenderers are to refer to the Model Preambles for Trades
(Latest Edition) and Supplementary Preambles for further
description and amplification of work in this section
SUPPLEMENTARY PREAMBLES
Descriptions of bolts shall be deemed to include
nuts and washers
Descriptions of expansion anchors and bolts and
chemical anchors and bolts shall be deemed to include
nuts, washers and mortices in brickwork or concrete
Metalwork described as "holed for bolt(s)" shall be deemed
to exclude the bolts unless otherwise described
EXCAVATIONS, FILLING, ETC
EXCAVATION
1 | Excavate foundation pits for raft foundation |  | m3 | 8
COMPACTION
2 | Backfill with G6 material from commercial sources |  | m3 | 8
compacted to 95% MOD AASTO in layers not
exceeding 150mm at +/-2% OMC in foundation, under
slabs and any other disgnated areas
BILL No. 3
Bill No. 3 EARTHWORKS carried to summary

## Bill 4
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 4
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 4
CONCRETE, FORMWORK AND REINFORCEMENT
| Notes: 1. | Tenderers are advised to study the 'Construction
specification PW371-A and B as amended
(downloadable from Department of Public Works
website, www.publicworks.gov.za) before pricing
this bill 4. Unless otherwise stated all items in this Bill
FORMWORK
1 | Raft foundation beams |  | m2 | 4.6
REINFORCED CONCRETE
2 | 150mm thick raft foundation slab |  | m3 | 3
REINFORCEMENT
3 | Wire mesh Ref. 245 |  | m2 | 4
BILL No. 4
Bill No. 4 CONCRETE, FORMWORK AND REINFORCEMENT carried to Summary

## Bill 5
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 5
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 5
WATERPROOFING
| Notes: 1. | Tenderers are to refer to the Model Preambles for
Trades (Latest Edition) and Supplementary Preambles
for further description and amplification of work in this
section
SUPPLEMENTARY PREAMBLES
Waterproofing of roofs, basements, etc shall be laid under a ten
year guarantee. Waterproofing to roofs shall be laid to even
falls to outlets etc with necessary ridges, hips and valleys.
Descriptions of sheet or membrane waterproofing shall be
deemed to include additional labour to turn-ups and turn-downs
WATERPROOFING TO ROOFS, BASEMENTS, ETC
Prime with one coat bitumen primer and one layer 4mm fully
bonded waterproof membrane comprising two bitumen
layers reinforced with woven spunbonded polyester fabric
and coated with polyethelene film for heat bonding, laid with
100mm side and 150mm end laps
1 | On flat roofs |  | m2 | 250
PROTECTIVE ROOFING PAINT
Two coats bituminous aluminium paint
2 | On flat roofs |  | m2 | 250
DAMPPROOFING OF WALLS AND FLOORS
Repair damp course by using injectable Damp Proof Course
(DPC) to treat rising damp.
All to specialist specification and details.
3 | On internal walls |  | m2 | 220
4 | Allow for painting of damp repair |  | m2 | 220
BILL No. 5
Bill No. 5 WATERPROOFING carried to Summary

## Bill 6
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 6
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO 6
ROOF COVERINGS ETC
| Notes: 1. | Tenderers are advised to study the 'Construction
specification PW371-A and B as amended
(downloadable from Department of Public Works
website, www.publicworks.gov.za) before pricing
this bill 6. Unless otherwise stated all items in this Bill
SUPPLEMENTARY PREAMBLES
Straight cutting
Descriptions of all roof coverings are deemed to
cutting
PROFILED METAL SHEETING AND ACCESSORIES
Where roof coverings are fixed on top of rigid board
insulation to purlins etc, descriptions of roof
coverings shall include therefore:
ROOF AND WALL INSULATION - NON ROOF SLAB AREAS
ROOF
Chromadek® klip tite roof sheeting coated outside
and galvinized inside 0.58mm min.thickness on
38x38mm battens @ 800mm centre max on 114x38mm
truss @950mm centre max. Colour Charcoal
1 | Supplying, delivery and installation of concrete roofing tiles |  | m2 | 660
BILL No. 6
Bill No. 6 ROOF COVERINGS ETC carried to Summary

## Bill 7
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 7
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 7
CARPENTRY & JOINERY
| Notes: 1. | Tenderers are advised to study the 'Construction
specification PW371-A and B as amended
(downloadable from Department of Public Works
website, www.publicworks.gov.za) before pricing
this bill 7. Unless otherwise stated all items in this Bill
SUPPLEMENTARY PREAMBLES
Joinery Descriptions of frames shall be deemed to
include frames, transomes, mullions, rails, etc
Descriptions of hardwood joinery shall be deemed to
include pelleting of bolt holes
Fixing Items described as "nailed" shall be deemed
to be fixed with hardened steel nails or shot pins to
brickwork or concrete
Decorative laminate finish Laminate finish shall be
glued under pressure. Edge strips shall be butt
jointed at junctions with adjacent similar finish
WALLS, ETC
2 | Timber partition panell wall to match existing |  | m2 | 15
3 | Timber frame to match existing |  | m | 48.72
WINDOWS, DOORS, FRAMES,ETC
Window frames
5 | Window frame 1930 x 1240 mm |  | No. | 1
6 | Window frame 1910 x 1305 mm |  | No. | 1
7 | Window frame 1540 x 1085 mm |  | No. | 1
8 | Window frame 555 x 1330 mm |  | No. | 1
Doors
9 | Timber door to match existing |  | No. | 1
10 | Timber frame to match existing |  | No. | 1
CEILING, ETC
11 | Ceiling boards and cornices |  | m2 | 4
BILL No. 7
Bill No. 7 CARPENTRY & JOINERY carried to Collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 7
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
FITTINGS
12 | Counter top to match existing |  | No. | 1
13 | Shelves to match existing |  | No. | 1
BILL No. 7
Bill No. 7 CARPENTRY & JOINERY carried to Collection
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 7
ITEM | PAYMENT |  | Page No.
NO | REFERS |  |  |  |  | AMOUNT
TO
ALTERATIONS
COLLECTION
| Total Brought Forward from Page No. |  | 1
2
BILL No. 7
Bill No. 7 CARPENTRY & JOINERY carried to Collection

## Bill 8
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 8
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 8
IRONMONGERY
| Notes: 1. | Tenderers are advised to study the 'Construction
specification PW371-A and B as amended
(downloadable from Department of Public Works
website, www.publicworks.gov.za) before pricing this
bill 8. Unless otherwise stated all items in this Bill
SUPPLEMENTARY PREAMBLES
Finishes to ironmongery
Where applicable finishes to ironmongery are
indicated by suffixes in accordance with the following
list: BS Satin bronze lacquered CH Chromium plated SC
Satin chromium plated SE Silver enamelled GE Grey
enamelled AS Anodised silver AB Anodised bronze AG
LOCKS
UNION' or other approved
1 | Client approved stainless steel lock set |  | No. | 1
HANDLES
UNION' or other equal and approved
2 | Union' or similar approved door handles |  | Pair | 1
BILL No. 8
Bill No. 8 IRONMONGERY carried to collection

## Bill 9
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 9
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 9
METALWORK
Tenderers are to refer to the Model Preambles for Trades
(Latest Edition) and Supplementary Preambles for further
description and amplification of work in this section
SUPPLEMENTARY PREAMBLES
Descriptions of bolts shall be deemed to include nuts and
washers
Descriptions of expansion anchors and bolts and chemical
anchors and bolts shall be deemed to include nuts, washers
and mortices in brickwork or concrete
Metalwork described as "holed for bolt(s)" shall be deemed to
exclude the bolts unless otherwise described
OTHER METALS
ALMINIUM WINDOWS, DOORS, ETC
Standard class A2 heavy duty aluminium framed
sliding door panel as for AAAMSA specifications
Purpose made powdercoated aluminium window
complete with all necessary beading, rubber seals,
drip sections & neoprine gaskets to allen keyed
Secured as per manufactures's spec.
6.5mm clear sheet safety glass requirements of
SANS 10137, SANS 10400 and produced to SANS 50572
and SANS 1263. All glazing to conform to NHBRC
specifications
Claw lock to folding door
Sliding gear & floor guide by manufacturer
Client approved stainless steel lock set
1 | Supplying, delivery and installation |  | m2 | 250
of aluminum work for windows and doors
2 | Turnstiles swing gate |  | No. | 1
BILL No. 9
Bill No. 9 METALWORK carried to Summary

## Bill 10
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 10
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 10
TILING
| Notes: 1. | Tenderers are advised to study the 'Construction
specification PW371-A and B as amended
(downloadable from Department of Public Works
website, www.publicworks.gov.za) before pricing this
bill 10. Unless otherwise stated all items in this Bill
SUPPLEMENTARY PREAMBLES
Descriptions Unless described as "fixed with adhesive to
plaster (plaster elsewhere)" descriptions of tiling on brick or
concrete walls, columns, etc shall be deemed to include
1:4 cement plaster backing and descriptions of tiling on
concrete floors etc
FLOOR TILING
Supply, delivery and fixing of tiles allowing for all
adhesives, grouts, labours and the like:
Internal floor areas
1 | On floors |  | m² | 4
2 | On skirtings |  | m | 8
BILL No. 10
Bill No. 10 TILING carried to Summary

## Bill 11
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 11
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 11
PLUMBING AND DRAINAGE
| Notes: 1. | Tenderers are advised to study the
specification PW371-A and B as amended
Construction (downloadable from Department
of Public Works website,
www.publicworks.gov.za) before pricing this
bill 11. Unless otherwise stated all items in this
Bill
SUPPLEMENTARY PREAMBLES
All fittings to be installed with silicon contact joint
between the fitting and the finished wall, floor or
vanity surface
Descriptions shall be deemed to include jointing,
shortlengths, nipples and running joints such as sockets,
collars,couples. Descriptions shall be deemed to
include bending, jointing pipes of differing material and
jointing pipes to taps, valves traps,etc Descriptions
shall be deemed to include pipe supports such as clips
, saddles, holderbats, hanger, etc. Descriptions shall
be deemed to include holes for pipes and cutting and
fittings around pipes unless otherwise stated by the
Employer's agent.
RAINWATER DISPOSAL
Roof gutters, rainwater pipes, etc
1 | Roof gutters |  | m | 283.31
2 | Rainwater pipe to match existing |  | m² | 3.3
3 | Extra over pipe for angle |  | No. | 4
BILL No. 11
Bill No. 11 TILING carried to Summary

## Bill 12
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 12
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 12
ELECTRICAL WORKS
ELECTRICAL INSTALLATIONS
1 | 12 way surface DB |  | No. | 1
2 | 63 AMP double pole MCB |  | No. | 1
3 | 63 AMP earth leakage |  | No. | 1
4 | 20 AMP MCB |  | No. | 3
5 | 15 AMP MCB |  | No. | 1
6 | 4x2 extension box |  | No. | 1
7 | 4x2 One lever switch |  | No. | 4
8 | 4x4 15 AMP socket outlet |  | No. | 5
9 | 4x4 30 AMP isolator |  | No. | 1
10 | 4x2 30 AMP isolator |  | No. | 1
11 | Light fittings |  | No. | 5
12 | 50x50mm trunking |  | m | 10
13 | 5x20mm 6u80 nail in nylon C8K |  | Item
14 | 20x20mm PVC trunking |  | m | 12
15 | 2,5mm2 cable (twin and flat) |  | Item
BILL No. 12
Bill No. 12 ELECTRICAL WORKS carried to Collection

## Bill 13
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 13
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 13
GLAZING
Tenderers are to refer to the Model Preambles for Trades
(Latest Edition) and Supplementary Preambles for further
description and amplification of work in this section
SUPPLEMENTARY PREAMBLES
WINDOWS, DOORS, ETC
Glazing to match existing
1 | Window 1930 x 1240 mm |  | m | 2.393
2 | Window 1910 x 1305 mm |  | m | 2.74
3 | Window 1540 x 1085 mm |  | m | 1.84
4 | Window 555 x 1330 mm |  | m | 0.804
6 | Window 620 x 14200 mm |  | m | 0.937
BILL No. 13
Bill No. 12 GLAZING carried to summary

## Bill 14
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  |  |  | Bill
Q9308 | [5 empty] | 14
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 14
PAINTWORK
| Notes: 1. | Tenderers are advised to study the specification
PW371-A and B as amended Construction
(downloadable from Department of Public Works
website, www.publicworks.gov.za) before pricing
this bill 14. Unless otherwise stated all items in
Bill this
SUPPLEMENTARY PREAMBLES
DESCRIPTIONS
Descriptions of paintwork shall be deemed to include
for all cutting in
PREPARATORY WORK TO EXISTING WORK
Previously painted plastered surfaces shall be thoroughly
washed down with polycell sugar-soap solution, rinse with
clean water to remove all traces of soap, sand glossy surface
to a matt finish and allowed to dry 'completely for 24 hours
before any
Previously painted metal surfaces shall be cleaned of all rust,
scale and dirt, removed by scraping or with steel brushes. All
oil and grease shall be removed and perfectly clean surfaces
obtained. If necessary, the surfaces shall be de-grease
Previously painted wood surfaces shall be thoroughly
cleaned down. Blistered or peeling paint shall be completely
removed and cracks and crevices shall be primed, filled with
suitable filler and finished smooth
ON METAL SURFACES
One coat alkyd based zinc phosphate primer and two
coats premium quality polyurethane enamel paint,
on steel
ROOF, ETC
1 | Corrugated roofing sheets |  | m² | 660
WOOD SURFACES
2 | Timber panels and frames |  | m² | 25
BILL No. 14
Bill No. 14 PAINTWORK carried to collection

## BOQ - Summary
CONTRACT NUMBER: |  | ROOF & SHOPFRONT REPLACEMENT & GATE 2 TK OFFICE THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN, CAPE TOWN |  | SUMMARY
Q9308
Item |  | DESCRIPTION |  | AMOUNT
No.
BILL NO. 1 |  |  | PRELIMINARIES AND GENERAL
BILL NO. 2 |  |  | ALTERATIONS TO EXISTING BUILDING
BILL NO. 3 |  |  | EARTHWORKS
BILL NO. 4 |  |  | CONCRETE, FORMWORK AND REINFORCEMENT
BILL NO. 5 |  |  | WATERPROOFING
BILL NO 6 |  |  | ROOF COVERINGS ETC
BILL NO. 7 |  |  | CARPENTRY & JOINERY |  | 0
BILL NO. 8 |  |  | IRONMONGERY
BILL NO. 9 |  |  | METALWORK
BILL NO. 10 |  |  | TILING
BILL NO. 11 |  |  | PLUMBING AND DRAINAGE
BILL NO. 12 |  |  | ELECTRICAL WORKS |  | 0
BILL NO. 13 |  |  | GLAZING
BILL NO. 14 |  |  | PAINTWORK
SUBTOTAL
ADD CONTIGENCY
250000
TOTAL
ADD 15% VAT
TOTAL PROJECT CONSTRUCTION COSTS