## Bill 1
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
Item | DESCRIPTION |  |  |  |  | RATE
No. |  |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 1
PRELIMINARIES AND GENERAL
MEANING OF TERMS "TENDER / TENDERER"
Any reference to the words "Tender" or "Tenderer" herein and/or
in any other documentation shall be construed to have the same
meaning as the words "Bid" or "Bidder"
PRELIMINARIES
The JBCC Preliminaries, May 2018 edition for use with the JBCC
Principal Building Agreement Edition 6.2 is taken to be incorporated
herein. The tenderer is deemed to have referred to these
documents for the full intent and meaning of each clause. These
clauses are referred to by number and heading only. Where
standard clauses or options are not applicable to the contract such
modifications or corrections as are necessary are given under each
relevant clause. Where an item is not relevant to this specific
contract such item is marked "N/A" signifying "Not Applicable"
PRICING OF PRELIMINARIES
Should Option A, as set out in clause B10.3.1 hereinafter be used
for the adjustment of preliminaries then each item priced is to be
allocated to one or more of the three categories Fixed, Value
Related or Time Related the spaces provided under each item
Items not priced in these Preliminaries shall be deemed to be
included elsewhere in these Bills of Quantities
SECTION A: JBCC PRINCIPAL BUILDING AGREEMENT
DEFINITIONS AND INTERPRETATION
1 | A1.0 | DEFINITIONS AND INTERPRETATION
Clause 1.0
| Clause 1.1 |  | Definition of "Commencement Date" is added:
"COMMENCEMENT DATE" means the date that the agreement,
made in terms of the Form of Offer and Acceptance, comes into effect
Clause 1.1 Definition of "Construction Guarantee" is amended by
replacing it with the following:
"CONSTRUCTION GUARANTEE" means a guarantee at call
obtained by the contractor from an institution approved by the
employer in terms of the employer's construction guarantee form as
selected in the schedule
Clause 1.1 Definition of "Construction Period" is amended by
replacing it with the following:
"CONSTRUCTION PERIOD" means the period commencing on the
commencement date and ending on the date of practical completion
"CORRUPT PRACTICE" means the offering, giving, receiving or
soliciting of anything of value to influence the action of a public
official in the procurement process or in contract execution
Clause 1.1 Definition of "Corrupt Practice" is added:
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  |  |  | RATE
NO | REFERS |  |  | UNIT | QUANTITY |  | AMOUNT
TO
Clause 1.1 Definition of "Fraudulent Practice" is added:
"FRAUDULENT PRACTICE" means a misrepresentation of facts in
order to influence a procurement process or the execution of a
contract to the detriment of any tenderer and includes collusive
practice among tenderers (prior to or after the tender submission)
designed to establish tender prices at artificial non- competitive
levels and to deprive the tenderer of the benefits of free and open
competition
| Clause 1.1 |  | Definition of "Interest" is amended by replacing it with
"INTEREST" means the interest rates applicable on this contract,
whether specifically indicated in the relevant clauses or not, will be
the rate as determined by the Minister of Finance, from time to
time, in terms of section 80(1)(b) of the Public Finance Management
Act, 1999 (Act No. 1 of 1999)
| Clause 1.1 |  | Definition of "Principal Agent" is amended by
replacing it with the following:
"PRINCIPAL AGENT" means the person or entity appointed by the
employer and named in the schedule. In the event of a principal
agent not being appointed, then all the duties and obligations of a
principal agent as detailed in the agreement shall be fulfilled by
a representative of the employer as named in the schedule
| Clause 1.1 |  | Definition of "Security" is amended by replacing it with
the following:
"SECURITY" means the form of security provided by the employer
or contractor, as stated in the schedule, from which the contractor
or employer may recover expense or loss
No clause
| Fixed:________Value related:_________Time related:_________ |  |  | Item
2 | A2.0 |  | LAW, REGULATIONS AND NOTICES
Clause 2.0
Note: A separate clause has been included in Section C : Specific
Preliminaries of the bills of quantities / lump sum document for the
contractor to have the opportunity to price for all the requirements of
the Occupational Health and Safety Act, Construction Regulations
and Health and Safety Specification
| Fixed:________Value related:_________Time related:_________ |  |  | Item
3 | A3.0 |  | OFFER AND ACCEPTANCE
Clause 3.0
| Fixed:________Value related:_________Time related:_________ |  |  | Item
4 | A4.0 |  | CESSION AND ASSIGNMENT
Clause 4.0
| Fixed:________Value related:_________Time related:_________ |  |  | Item
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  |  |  | RATE
NO | REFERS |  |  | UNIT | QUANTITY |  | AMOUNT
TO
5 | A5.0 |  | DOCUMENTS
Clause 5.0
Clause 5.7 is amended by the addition of the following:
The contractor shall supply and keep a copy of the JBCC Series 2000
Principal Building Agreement and Preliminaries applicable to this
contract on the site, to which the employer, principal agent and agents
shall have access at all times
| Fixed:________Value related:_________Time related:_________ |  |  | Item
6 | A6.0 |  | EMPLOYER'S AGENTS
Clause 6.0
Clause 6.1 is amended by the addition of the following:
This clause is amended to include clauses 26.7 in terms of which the
employer has retained its authority and has not given a mandate to the
principal agent and in terms of which the employer sign all documents
| Fixed:________Value related:_________Time related:_________ |  |  | Item
7 | A7.0 |  | DESIGN RESPONSIBILITY
Clause 7.0
Clause 7.3 is amended by replacing it with the following:
No clause
| Fixed:________Value related:_________Time related:_________ |  |  | Item
INSURANCES AND SECURITIES
8 | A8.0 |  | WORKS RISK
Clause 8.0
| Fixed:________Value related:_________Time related:_________ |  |  | Item
9 | A9.0 |  | INDEMNITIES
Clause 9.0
| Fixed:________Value related:_________Time related:_________ |  |  | Item
10 | A10.0 |  | INSURANCES
Clause 10.0
| Clause 10.0 |  | is amended by the addition of the following clauses:
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  |  |  | RATE
NO | REFERS |  |  | UNIT | QUANTITY |  | AMOUNT
TO
| 10.11 |  | Damage to the Works
| (a) |  | Without in any way limiting the contractor's obligations
in terms of the contract, the contractor shall bear the
full risk of damage to and/or destruction of the works
by whatever cause during during construction of the
works and hereby indemnifies and holds harmless the
employer against any such damage. Thecontractor
shall take such precautions and security measures and
other steps for the protection and security of the works
as the contractor may deem necessary
| (b) |  | The contractor shall at all times proceed immediately
to remove or dispose of any debris arising from damage
to or destruction of the works and to rebuild, restore,
replace and/or repair the works
| (c) |  | The employer shall carry the risk of damage to or
destruction of the works and materials paid for by the
employer that is the result of the excepted risks as set
out in 10.12
| (d) |  | Where the employer bears the risk in terms of this
contract, the contractor shall, if requested to do so,
reinstate any damage or destroyed portions of the
works and the costs of such reinstatement shall be
measured and valued in terms of 27.0 hereof
| 10.12 |  | Injury to Persons or loss of or damage to
Properties
| (a) |  | The contractor shall be liable for and hereby
indemnifies the employer against any liability, loss,
claim or proceeding whether arising in common law or
by statute, consequent upon personal injuries to or the
death of any person whomsoever arising out of or in
the course of or caused by the execution of the works
unless due to any act or negligence of any person for
whose actions the employer is legally liable
| (b) |  | The contractor shall be liable for and hereby
indemnifies the employer against any liability, loss,
claim or proceeding consequent upon loss of or
damage to any moveable or immovable or personal
property or property contiguous to the site, whether
belonging to or under the control of the employer or
any other body or person, arising out of or in the
course of or by reason of the execution of the works
unless due to any act or negligence of any person for
whose actions the employer is legally liable
| (c) |  | The contractor shall, upon receiving a contract
instruction from the principal agent, cause the same
to be made good in a perfect and workmanlike manner
at his own cost and in default thereof the employer shall
be entitled to cause it to be made good and to recover
he cost thereof from the contractor or to deduct the
same from amounts due to the contractor
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  |  |  | RATE
NO | REFERS |  |  | UNIT | QUANTITY |  | AMOUNT
TO
| (d) |  | The contractor shall be responsible for the protection
and safety of such portions of the premises placed
under his control by the employer for the purpose of
executing the works until the issue of the certificate of
practical completion
| (e) |  | Where the execution of the works involves the risk of
removal of or interference with support to adjoining
properties including land or structures or any structures
to be altered or added to, the contractor shall obtain
adequate insurance and will remain adequately insured
or insured to the specific limit stated in the contract
against the death of or injury to persons or damage to
such property consequent on such removal or
interference with the support until such portion of the
works has been completed
| (f) |  | The contractor shall at all times proceed immediately
at his own cost to remove or dispose of any debris and
to rebuild, restore, replace and/or repair such property
and to execute the works
| 10.13 |  | High risk insurance
In the event of the project being executed in a geological
area classified as a "High Risk Area", that is an area which
is subject tohighly unstable subsurface conditions that
might result in catastrophic ground movement evident by
sinkhole or doline formation the following will apply:
| 10.13.1 |  | Damage to the works
The contractor shall, from the commencement date of the
works until the date of the certificate of practical completion
bear the full risk of and hereby indemnifies and holds
harmless the employer against any damage to and/or
destruction of the works consequent upon a catastrophic
ground movement as mentioned above. The contractor
shall take such precautions and security measures and
other steps for the protection of the works as he may deem
necessary
When so instructed to do so by the principal agent, the
contractor shall proceed immediately to remove and/or
dispose of any debris arising from damage to or destruction
of the works and to rebuild, restore, replace and/or repair
the works, at the contractor's own costs
| 10.13.2 |  | Injury to persons or loss of or damage to property
The contractor shall be liable for and hereby indemnifies
and holds harmless the employer against any liability, loss,
claim or proceeding arising at any time during the period of
the contract whether arising in common law or by statute,
consequent upon personal injuries to or the death of any
person whomsoever resulting from, arising out of, or
caused by a catastrophic ground movement as mentioned
above
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION
NO | REFERS | [5 empty] | AMOUNT
TO
The contractor shall be liable for and hereby indemnifies
the employer against any and all liability, loss, claim or
proceeding consequent upon loss of or damage to any
moveable or immovable or personal property or property
contiguous to the site, whether belonging to or under the
control of the employer or any other body or person
whomsoever arising out of or caused by a catastrophic
ground movement, as mentioned above, which occurred
during the period of the contract
| 10.13.3 | It is the responsibility of the contractor to ensure that he
has adequate insurance to cover his risk and liability as
mentioned in 10.7.1 and 10.7.2. Without limiting the
contractor's obligations in terms of the contract, the
contractor shall, within twenty-one (21) calendar days of the
commencement date but before commencement of the
works, submit to the employer proof of such insurance
policy, if requested to do so
| Fixed:________Value related:_________Time related:_________ |  |  | Item
11 | A11.0 |  | SECURITIES
Clause 11.0
Clauses 11.1 - 11.10 are amended by replacing them with the
following
| 11.1 | In respect of contracts with a contract sum up to R1 million,
the security to be provided by the contractor to the
employer will be a payment reduction of five per cent (5%)
of the value certified in the payment certificate
(excluding VAT)
| 11.1.1 | The payment reduction of the value certified in a payment
certificate shall be mutatis mutandi in terms
| 11.1.2 | The employer shall be entitled to recover expense and loss
from the payment reduction in terms of 27.0 provided that
the employer complies with the provisions of 27.4 in which
event the employer's entitlement shall take precedence
over his obligations to refund the payment reduction
security or portions thereof to the contractor
| 11.2 | In respect of contracts with a contract sum above
R1 million, the contractor shall have the right to select the
security to be provided in terms of 11.3, 11.4, 11.5, 14.6,
or 11.7 as stated in the schedule. Such security shall be
provided to the employer within twenty-one (21) calendar
days from commencement date. Should the contractor
fail to select the security to be provided or should the
contractor fail toprovide the employer with the selected
security within twenty-one (21) calendar days from
commencement date, the security in terms of 11.7
shall be deemed to have been selected
| 11.3 | Where security as a cash deposit of ten per cent (10%) of
the contract sum (excluding VAT) has been selected:
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
Item | DESCRIPTION |  |  |  |  | RATE
No. |  |  |  | UNIT | QUANTITY |  | AMOUNT
| 11.3.1 | The contractor shall furnish the employer with a cash
deposit equal in value to ten per cent (10%) of the contract
sum (excluding VAT) within twenty- one (21) calendar
days from commencement date
| 11.3.2 | Within twenty-one (21) calendar days of the date of
practical completion of the works the employer shall
reduce the cash deposit to an amount equal to three
percent (3%) of the contract value (excluding VAT), and
refund the balance to the contractor
| 11.3.3 | Within twenty-one (21) calendar days of the date of final
completion of the works the employer shall reduce the
cash deposit to an amount equal to one per cent (1%) of
the contract value (excluding VAT) and refund the
balance to the contractor
| 11.3.4 | On the date of payment of the amount in the final payment
certificate, the employer shall refund the remainder of
the cash deposit to the contractor
| 11.3.5 | The employer shall be entitled to recover expense and loss
from the cash deposit in terms of 33.0 provided that the
employer complies with the provisions of 33.4 in which
event the employer's entitlement shall take precedence
over his obligations to refund the cash deposit security or
portions thereof to the contractor
| 11.3.6 | The parties expressly agree that neither the employer nor
the contractor shall be entitled to cede the rights to the
deposit to any third party
| 11.4 | Where security as a variable construction guarantee of
ten percent (10%) of the contract sum (excluding VAT) has
been selected:
| 11.4.1 | The contractor shall furnish the employer with an
acceptable variable construction guarantee equal in
value to ten per cent (10%) of the contract sum
(excluding VAT) within twenty-one (21) calendar days from
commencement date
Clause 11.4.1 is deemed to be amended by the addition of the
following sentence;
No interest will be paid on such amounts withheld
| 11.4.2 | The variable construction guarantee shall reduce and
expire in terms of the Variable Construction Guarantee
form included in the invitation to tender
| 11.4.3 | The employer shall return the variable construction
guarantee to the contractor within fourteen (14) calendar
days of it expiring
| 11.4.4 | Where the employer has a right of recovery against the
contractor in terms of 33.0, the employer shall issue a
written demand in terms of the variable construction
guarantee
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  |  |  | RATE
NO | REFERS |  |  | UNIT | QUANTITY |  | AMOUNT
TO
| 11.5 | Where security as a fixed construction guarantee of five
percent (5%) of the contract sum (excluding VAT) and a
five per cent (5%) payment reduction of the value certified
in the payment certificate (excluding VAT) has been
selected:
| 11.5.1 | The contractor shall furnish a fixed construction
guarantee to the employer equal in value to five per cent
(5%) of the contract sum (excluding VAT)
| 11.5.2 | The fixed construction guarantee shall come into force on
the date of issue and shall expire on the date of the last
certificate of practical completion
| 11.5.3 | The employer shall return the fixed construction
guarantee to the contractor within fourteen (14)
calendar days of it expiring
| 11.5.4 | The payment reduction of the value certified in a payment
certificate shall be in terms of clause 25.
| 11.5.5 | Where the employer has a right of recovery against the
contractor in terms of 27.0, the employer shall be entitled
to issue a written demand in terms of the fixed
construction guarantee or may recover from the
payment reduction or may do both
| 11.6 | Where security as a cash deposit of five per cent (5%) of
the contract sum (excluding VAT) and a payment
reduction of five per cent (5%) of the value certified in the
payment certificate (excluding VAT) has been selected:
| 11.6.1 | The contractor shall furnish the employer with a cash
deposit equal in value to five per cent (5%) of the contract
sum (excluding VAT) within twenty- one (21) calendar days
from commencement date
| 11.6.2 | Within twenty-one (21) calendar days of the date of
practical completion of the works the employer shall
refund the cash deposit in total to the contractor
| 11.6.3 | The payment reduction of the value certified in a payment
certificate shall be mutatis mutandi in terms of 25
| 11.6.4 | Where the employer has a right of recovery against the
contractor in terms of 27.0, the employer may issue a
written notice in terms of 27.4 or may recover from the
payment reduction or may do both
| 11.7 | Where security as a payment reduction of ten percent
(10%) of the value certified in the payment certificate
(excluding VAT) has been selected:
| 11.7.1 | The payment reduction of the value certified in a payment
certificate shall be mutatis mutandi in terms of 25
| 11.7.2 | The employer shall be entitled to recover expense and
loss from the payment reduction in terms of 27.0 provided
that the employer complies with the provisions of 27.4 in
which event the employer's entitlement shall take
precedence over his obligations to refund the payment
reduction or portions thereof to the contractor
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  |  |  | RATE
NO | REFERS |  |  | UNIT | QUANTITY |  | AMOUNT
TO
| 11.8 | Payments made by the guarantor to the employer in terms
of the fixed or variable construction guarantee shall not
prejudice the rights of the employer or contractor in terms
of this agreement
| 11.9 | 11.9 Should the contractor fail to furnish the security in terms
of 11.2, the employer, in his sole discretion and without
notification to the contractor, is entitled to change the
contractor's selected form of security to that of a ten per cent
(10%) payment reduction of the value certified in the
payment certificate (excluding VAT), whereafter 11.7 shall be
applicable
| Fixed:________Value related:_________Time related:_________ |  |  | Item
EXECUTION
12 | A12.0 |  | OBLIGATIONS OF THE PARTIES
Clause 12.0
Clause 12.1.1 is amended by replacing it with:
No clause
Clause 12.2.4 is amended by the addition of the following clause:
| 12.2.4 | An acceptable health and safety plan, required in terms of
the Occupational Health and Safety Act, 1993
(Act 85 of 1993), within twenty-one (10) calendar days of
commencement date
Clause 12.2.7 is amended by replacing it with the following clause:
Give the contractor possession of the site within ten (10) working days
of the contractor complying with the terms of 12.2.4
| Fixed:________Value related:_________Time related:_________ |  |  | Item
13 | A13.0 |  | SETTING OUT OF THE WORKS
Clause 13.0
| Fixed:________Value related:_________Time related:_________ |  |  | Item
14 | A14.0 |  | NOMINATED SUBCONTRACTORS
Clause 14.0
Clause 14.1.5 is amended by replacing it with the following:
Note: See item B9.1 hereinafter for adjustment of attendance on
nominated subcontractors executing work allowed for under
provisional sums
| Fixed:________Value related:_________Time related:_________ |  |  | Item
15 | A15.0 |  | SELECTED SUBCONTRACTORS
Clause 15.0
Clause 15.1.2 to 15.5 and 15.2 to 15.5 is amended by replacing it
with:
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION
NO | REFERS | [5 empty] | AMOUNT
TO
The Contractor and principal agent shall appoint a selected
subcontractor in accordance with the CIDB practice #7
| Fixed:________Value related:_________Time related:_________ |  |  | Item
16 | A16.0 |  | DIRECT CONTRACTORS
Clause 16.0
| Fixed:________Value related:_________Time related:_________ |  |  | Item
17 | A17.0 |  | CONTRACT INSTRUCTIONS
Clause 17.0
| Fixed:________Value related:_________Time related:_________ |  |  | Item
COMPLETION
18 | A18.0 |  | INTERIM COMPLETION
Clause 18.0
| Fixed:________Value related:_________Time related:_________ |  |  | Item
19 | A19.0 |  | PRACTICAL COMPLETION
Clause 19.0
| Fixed:________Value related:_________Time related:_________ |  |  | Item
20 | A20.0 |  | COMPLETION IN SECTIONS
Clause 20.0
| Fixed:________Value related:_________Time related:_________ |  |  | Item
21 | A21.0 |  | DEFECTS LIABILITY PERIOD AND FINAL COMPLETION
Clause 21.0
Add the following to the end of sub-clause 21.1.2:
“All civil, electrical, electronic, HVAC, fire detection, gas suppression
and other specialist installations are subject to a three hundred and
sixty-five (365) calendar days defects liability and maintenance period.
The contractor shall attend to defects during the works completion and
defects liability periods on a progressive basis, to the satisfaction of
the principal agent and will not be permitted to wait until the end of the
defects liability period or until the amount of defects accumulate in
order to attend to a comprehensive list of defects.”
| Fixed:________Value related:_________Time related:_________ |  |  | Item
22 | A22.0 |  | LATENT DEFECTS LIABILITY PERIOD
Clause 22.0
| Fixed:________Value related:_________Time related:_________ |  |  | Item
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION
NO | REFERS | [5 empty] | AMOUNT
TO
23 | A23.0 |  | REVISION OF DATE FOR PRACTICAL COMPLETION
Clause 23.0
| (i) | The addition of the following clauses:-
Sub-clause 23.9
“Revision to the date for practical completion shall only be
considered when work on the critical path of the agreed
programme for the works is delayed.”
| (ii) | Sub-clause 23.10 – Acceleration
Sub-clause 23.10.1
“Irrespective of whether or not the principal agent rules that
the contractor is entitled to an extension of time or a revision
of the date for practical completion, the principal agent shall
nevertheless, at any time, be entitled to instruct the contractor
in writing to accelerate the progress of the remaining works
to ensure that the works are completed by the original date
for practical completion or revised date as the case may be.”
Sub-clause 23.10.2
“Upon receipt of such instruction, the contractor shall take all
necessary steps to ensure that the works are completed
timeously including the provision by him of additional
resources, plant, manpower, etc and the working overtime or
additional overtime beyond that contemplated at the time of
tender (at all times adhering to the regulations and
requirements of all authorities) and by all other adequate and
proper means and methods. The contractor shall prove that
such steps are being taken if called upon to do so.”
Sub-clause 23.10.3
“The contractor’s entitlement to compensation arising out of
or in respect of any revision to the date for practical
completion that may have been granted by the principal
agent or alternatively where the principal agent has
instructed the contractor to accelerate, shall be adjudicated
strictly in terms of clause 32.”
| Fixed:________Value related:_________Time related:_________ |  |  | Item
24 | A24.0 |  | PENALTY FOR LATE AND NON-COMPLETION
Clause 24.0
| Fixed:________Value related:_________Time related:_________ |  |  | Item
PAYMENT
25 | A25.0 |  | PAYMENT
Clause 25.0
Notwithstanding this or any other clause, materials and goods stored
off site shall not be included in the amount authorized for payment.
The first sentence of sub-clause 25.10 is deemed to be deleted and
replaced with the following:
The employer shall pay the contractor the amount certified within
thirty (30) calendar days of the date.
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION
NO | REFERS | [5 empty] | AMOUNT
TO
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
26 | A26.0 |  | ADJUSTMENT TO THE CONTRACT VALUE
Clause 26.0
Adjustment to the contract value (Clause 26.0) Where prices are
submitted by the contractor or nominated/selected subcontractors
during the progress of the works in respect of contract instructions or
in regard to a claim under the terms of the contract and
notwithstanding the fact that such prices may be used in an interim
payment certificate, there is to be no presumption of acceptance.
Should the principal agent wish to accept any such prices prior to the
issue of the final certificate, it will be in writing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
27 | A27.0 |  | ADJUSTMENT TO THE CONTRACT VALUE
Clause 27.0
Clause 27.2 is amended by adding the following sub-clauses:
| 27.2.11 | The contractor's failure or neglect to commence with
the works on the dates prescribed in the contract.
| 27.2.12 | The contractor's failure or neglect to proceed with the works
in terms of the contract.
| 27.2.13 | The contractor's failure or neglect for any reason to complete
the works in accordance with the contract.
| 27.2.14 | The contractor's refusal or neglect to comply strictly with any
of the conditions of contract or any contract instructions
and/or orders in writing given in terms of the contract.
| 27.2.15 | The contractor's estate being sequestrated or surrendered in
terms of the Insolvency laws in force within the Republic of South Africa."
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
SUSPENSION AND TERMINATION
28 | A28.0 |  | SUSPENSION BY CONTRACTOR
Clause 28.0
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
7 | A29.0 TERMINATION
Clause 29.0
Add the following sub-clauses 29.1.4 to 29.1.6 under 29.1 to read as
follows:
| 29.1.4 | The contractor’s refusal or neglect to comply strictly with
any of the conditions of contract.
| 29.1.5 | The contractor’s estate being sequestrated, liquidated or
surrendered in terms of the insolvency laws in force with
the Republic of South Africa.
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION
NO | REFERS | [5 empty] | AMOUNT
TO
| 29.1.6 | The contractor, in the judgment of the employer, has
engaged in corrupt or fraudulent practices in competing for
or in executing the contract.
Replace clause 29.3 with the following:
the employer may give notice of cancellation should the
contractor remain in default for ten (10) working days after
the date of of issue of such a notice of default
Clause 29.25.4
Replace “Sixty (60)” with “one hundred and twenty (120)”.
Add the following sub-clauses 29.29 under 29 to read as
follows: Notwithstanding any clause to the contrary, on
cancellation of this agreement either by the employer or the
contractor, or for any reason whatsoever, the contractor
shall on written instruction, discontinue with the works on a
stated date and withdraw himself from the site. The
contractor shall not be entitled to refuse to withdraw from
the works on the grounds of any lien or right of retention or
on the grounds of any other right whatsoever.
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
DISPUTE RESOLUTION
30 | A30.0 |  | DISPUTE RESOLUTION
Clause 30.0
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
SECTION B: JBCC PRELIMINARIES
B1.0 DISPUTE RESOLUTION
31 | B1.1 |  | Definitions and interpretation
See also clause A1.0 of Section A for additional and/or amended
definitions which shall apply equally to this Section
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
B2.0 DOCUMENTS
32 | B2.1 |  | Checking of documents
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
33 | B2.2 |  | Provisional bills of quantities
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
34 | B2.3 |  | Availability of construction documentation
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
35 | B2.4 |  | Interests of agents
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION
NO | REFERS | [5 empty] | AMOUNT
TO
36 | B2.5 |  | Priced documents
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
37 | B2.6 |  | Tender submission
Clause 2.6 is amended by replacing "JBCC Form of Tender" with
"Form of Offer and Acceptance"
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
B3.0 THE SITE
38 | B3.1 |  | Defined works area
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
39 | B3.2 |  | Geotechnical investigation
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
40 | B3.3 |  | Inspection of the site
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
41 | B3.4 |  | Existing premises occupied
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
42 | B3.5 |  | Previous work - dimensional accuracy
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
43 | B3.6 |  | Previous work - defects
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
44 | B3.7 |  | Services - known
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
45 | B3.8 |  | Services - unknown
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
46 | B3.9 |  | Protection of trees
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
47 | B3.10 |  | Articles of value
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
48 | B3.11 |  | Inspection of adjoining properties
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
B4.0 MANAGEMENT OF CONTRACT
49 | B4.1 |  | Management of the works
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
49 | B4.1 |  | Management of the works
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION
NO | REFERS | [5 empty] | AMOUNT
TO
50 | B4.2 |  | Programme for the works
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
51 | B4.3 |  | Progress meetings
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
52 | B4.4 |  | Technical meetings
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
53 | B4.5 |  | Labour and plant records
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
B5.0 SAMPLES, SHOP DRAWINGS AND MANUFACTURERS’ INSTRUCTIONS
54 | B5.1 |  | Samples of materials
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
55 | B5.2 |  | Workmanship samples
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
56 | B5.3 |  | Shop drawings
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
57 | B5.4 |  | Compliance with manufacturers' instructions
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
B6.0 TEMPORARY WORKS AND PLANT
58 | B6.1 |  | Deposits and fees
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
59 | B6.2 |  | Enclosure of the works
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
60 | B6.3 |  | Advertising
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
61 | B6.4 |  | Plant, equipment, sheds and offices
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
62 | B6.5 |  | Main notice board
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
63 | B6.6 |  | Subcontractors' notice board
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
B7.0 TEMPORARY SERVICES
64 | B7.1 |  | Location
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT
NO | REFERS | [5 empty] | AMOUNT
TO
65 | B7.2 |  | Water
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
66 | B7.3 |  | Electricity
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
67 | B7.4 |  | Telecommunication facilities
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
68 | B7.5 |  | Ablution facilities
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
B8.0 PRIME COST AMOUNTS
69 | B8.1 |  | Responsibility for prime cost amounts
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
B9.0 ATTENDANCE ON N/S SUBCONTRACTORS
70 | B9.1 |  | General attendance
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
71 | B9.2 |  | Special attendance
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
72 | B9.3 |  | Commissioning - fuel, water and electricity
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
B10.0 FINANCIAL ASPECTS
73 | B10.1 |  | Statutory taxes, duties and levies
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
74 | B10.2 |  | Payment for preliminaries
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
75 | B10.3 |  | Adjustment of preliminaries
Clauses B10.3.1 and B10.3.2 are amended by replacing "within
fifteen (15) working days of taking possession of the site" with "when
submitting his priced bills of quantities / lump sum document"
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
76 | B10.4 |  | Payment certificate cash flow
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
B11.0 GENERAL
77 | B11.1 |  | Protection of the works
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION
NO | REFERS | [5 empty] | AMOUNT
TO
78 | B11.2 |  | Protection / isolation of existing / sectionally
occupied works
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
79 | B11.3 |  | Security of the works
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
80 | B11.4 |  | Notice before covering work
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
81 | B11.5 |  | Disturbance
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
82 | B11.6 |  | Environmental disturbance
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
83 | B11.7 |  | Works cleaning and clearing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
84 | B11.8 |  | Vermin
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
85 | B11.9 |  | Overhand work
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
86 | B11.10 |  | Instruction manuals and guarantees
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
87 | B11.11 |  | As built information
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
88 | B11.12 |  | Tenant installations
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
B12.0 SCHEDULE OF VARIABLES
89 | B12.1 |  | Schedule of variables
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
This schedule contains all variables referred to in this document and
is divided into pre-tender and post-tender categories. The
pre-tender category must be completed in full and included in the
tender documents. Both the pre-tender and post-tender categories
form part of these Preliminaries
Spaces requiring information must be filled in, shown as
"not applicable" or deleted and not left blank. Where choices are
offered, the non-applicable items are to be deleted. Where
insufficient space is provided the information should be annexed
hereto and cross-referenced to the applicable clause of the
schedule. Key cross reference clauses are italicised in [ ] brackets
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION
NO | REFERS | [5 empty] | AMOUNT
TO
| 12.1 | PRE-TENDER INFORMATION
| 12.1.1 | Provisional bills of quantities
| [2.2] | The quantities are provisional
YES/NO
| 12.1.2 | Availability of construction documentation
| [2.3] | Construction documentation is complete
YES/NO
| 12.1.3 | Interests of agents
| [2.4] | Details:
| 12.1.4 | Defined works area
| [3.1] | Details:
| 12.1.5 | Geotechnical investigation
| [3.2] | Details:
| 12.1.6 | Existing premises occupied
| [3.4] | Details:
| 12.1.7 | Previous work - dimensional accuracy
| [3.5] | Details:
| 12.1.8 | Previous work - defects
| [3.6] | Details:
| 12.1.9 | Services - known
| [3.7] | Details:
| 12.1.10 | Protection of trees
| [3.9] | Details:
| 12.1.11 | Inspection of adjoining properties
| [3.11] | Details:
| 12.1.12 | Enclosure of the works
| [6.2] | Details:
| 12.1.13 | Offices
| [6.4.3] | Specific requirements:
The contractor shall provide, maintain and remove on
completion of the works an office for the exclusive use of
the principal agent, minimum size 4 x 3 x 3m high internally,
suitably insulated and ventilated, provided with electric
lighting and fitted with boarded floor, desk, chair, drawing
stool, drawing board and lock-up drawers for drawings. The
office shall be kept clean and fit for use at all times
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION
NO | REFERS | [5 empty] | AMOUNT
TO
| 12.1.14 | Main notice board
| [6.5] | Specific requirements:
The contractor shall provide, erect where directed, maintain
and remove on completion of the works a notice board size
3 x 3m as per Drawing, constructed of suitable boarding
with flat smooth surface and with edging bead 19mm thick
round outer edges and projecting 12mm from face of
boarding and rounded on front edge. The board shall be
securely fixed to hoarding, where hoarding is provided, or
fixed to and including a suitable supporting structure of
timber or tubular posts and braces. The board is to be
painted ivory white and the bead and 12mm wide dividing
lines dark green. All wording shall be inscribed in dark
green as per the coat of arms for SA. All wording shall be
inscribed in dark green painted sans serif lettering
| 12.1.15 | Subcontractors' notice board
| [7.2] | A notice board is required
YES/NO
Specific requirements:
| 12.1.16 | Water
| [7,3] | Option A (by contractor)
YES/NO
Option B (by employer - free of charge)
YES/NO
Option C (by employer - metered)
YES/NO
| 12.1.17 | Electricity
| [6.6] | Option A (by contractor)
YES/NO
Option B (by employer - free of charge)
YES/NO
Option C (by employer - metered)
YES/NO
| 12.1.18 | Telecommunications
| [7.4] | Option A (by contractor)
YES/NO
Option B (by employer - free of charge)
YES/NO
Option C (by employer - metered)
YES/NO
| 12.1.19 | Ablution facilities
| [7.5] | Option A (by contractor)
YES/NO
Option B (by employer)
YES/NO
| 12.1.20 | Protection of existing/sectionally occupied works
| [11.2] | Option A (by contractor)
YES/NO
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION
NO | REFERS | [5 empty] | AMOUNT
TO
| 12.1.21 | Special attendance
| [9.2] | Subcontractor (1) details:
Subcontractor (2) details:
Subcontractor (3) details:
Subcontractor (4) details:
| 12.1.22 | Special attendance
| [11.1] | Specific requirements:
| 12.1.23 | Disturbance
| [11.1] | Specific requirements:
The contractor shall keep the site, structures, etc
well-watered during operations to prevent dust and shall
provide and erect and remove on completion of the works
all necessary temporary dust screens all to the satisfaction
of the principal agent
| 12.1.24 | Environmental disturbance
| [11.6] | Specific requirements:
| 12.2 | POST-TENDER INFORMATION
| 12.1.19 | Payment of preliminaries
| [7.5] | Option A (prorated)
YES/NO
Option B (calculated)
YES/NO
| 12.2.2 | Adjustment of preliminaries
| [10.3] | Option A (prorated)
YES/NO
Option B (calculated)
YES/NO
| 12.2.3 | Additional agreed preliminaries items
Details:
SECTION C: SPECIFIC PRELIMINARIES
Section C contains specific preliminary items which apply to this
contract except where N/A (Not Applicable) appears against an item
90 | C1.0 | CONTRACT DRAWINGS
* Select relevant paragraph and delete whichever is not applicable
depending on whether the contract is based on a bills of quantities
or lump sum document
*The drawings issued with the tender documents do not comprise the
complete set but serve as a guide only for tendering purposes and for
indicating the scope of the work to enable the tenderer to acquaint
himself with the nature and extent of the works and the manner in
which they are to be executed
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION
NO | REFERS | [5 empty] | AMOUNT
TO
*A full set of drawings is issued with the tender documents indicating
the full scope of the work to enable the tenderer to acquaint himself
with the nature and extent of the works and the manner in which they
are to be executed
Should any part of the drawings not be clearly understood by the
tenderer he shall, before submitting his tender, obtain clarification in
writing from the principal agent
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
91 | C2.0 | GENERAL PREAMBLES
The document "Specification of Materials and Methods to be used
(PW371)" is obtainable on the Department's website
(http://www.publicworks.gov.za/ under "Consultants Guidelines"), and
shall be read in conjunction with the bills of quantities / lump sum
document and be referred to for the full descriptions of work to be
done and materials to be used
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
92 | C3.0 | TRADE NAMES
Wherever a trade name for any product has been described in the
bills of quantities / lump sum document, the tenderer's attention is
drawn to the fact that any other product of equal quality may be used
subject to the written approval of the principal agent being obtained
prior to the closing date for submission of tenders
If prior written approval for an alternative product is not obtained, the
product described shall be deemed to have been tendered for
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
93 | C4.0 | IMPORTED MATERIALS AND EQUIPMENT
Where imported items are listed in the tender documents, the
tenderer shall provide all the information called for, failing which the
price of any such item, materials or equipment shall be excluded from
currency fluctuations. (refer to Schedule of Imported Materials and
Equipment DPW-23(EC) to be completed by tenderer)
Notwithstanding any provisions elsewhere regarding the adjustment of
contract prices, the price of any item, material or equipment listed in
terms of this clause shall be excluded from the Contract Price
Adjustment Provisions (if applicable)
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
94 | C5.0 | IMPORTED MATERIALS AND EQUIPMENT
The site is situated in a security area and the tenderer must arrange
with the unit commander or other responsible officer to obtain
permission to enter the site for tendering purposes
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION
NO | REFERS | [5 empty] | AMOUNT
TO
95 | C6.0 | COMMENCEMENT OF WORKS IN SECURITY AREAS
As the works falls within a security area the contractor must give the
unit commander or other responsible officer notice before
commencement of the works. Should the contractor fail to make such
arrangements, admission to the site may be refused and any
additional costs will be for the contractor's account
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
96 | C7.0 | ENTRANCE PERMITS TO SECURITY AREAS
As the works falls within a security area the contractor shall obtain
entrance permits for his personnel and workmen entering the area and
shall comply with all regulations and instructions which may be issued
from time to time regarding the protection of persons and property
under the control of the Defence Force, Police or chief security officer
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
97 | C8.0 | SECURITY CHECK OF PERSONNEL
The principal agent may require the contractor to have his personnel
and workmen, or a certain number of them, security classified
In the event of the principal agent requesting the removal of a person
or persons from the works for security reasons, the contractor shall
do so forthwith and shall thereafter ensure that such person or
persons are denied access to the works and the site and/or to any
document or information relating to the works
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
98 | C9.0 | PROHIBITION ON TAKING OF PHOTOGRAPHS
In terms of article 119 of the Defence Act, 44 of 1957, it is prohibited
to sketch or to take photographs of any military site or installation or
any building or civil works thereon or to be in possession of a camera
or other apparatus used for taking of photographs except when
authorized thereto by or on behalf of the Minister
The same prohibition is also applicable to all correctional institutions
in terms of article 44.1(e) of the Correctional Services Act 8 of 1959
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
99 | C10.0 | HIV/AIDS AWARENESS
It is required of the contractor to thoroughly study the HIV/AIDS
Specification (PW 1544) of the Department that must be read
together with and is deemed to be incorporated under this Section
of the bills of quantities / lump sum document. Provision for
pricing of HIV/AIDS awareness is made under items C10.1 to C10.5
hereafter and it is explicitly pointed out that all requirements of the
aforementioned specification are deemed to be priced hereunder,
as the said items represent the only method of measurement and no
additional items or extras to the contract in this regard shall be
entertained
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION
NO | REFERS | [5 empty] | AMOUNT
TO
The contractor must take note that compliance with the HIV/AIDS
Specification is compulsory. In the event of partial or total
non-compliance, the principal agent, notwithstanding the provisions
of clause A 31.0 of Section A or any other clause to the contrary,
reserves the right to delay issuing any progress payment certificate
until the contractor provides satisfactory proof of compliance. The
contractor shall not be entitled to any compensation of whatsoever
nature, including interest, due to such delay of payment
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
100 | C10.1 | AWARENESS CHAMPION
Selection, appointment, briefing and making available of an
Awareness Champion including provision of all relevant services, all in
accordance with the HIV/AIDS Specification
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
101 | C10.2 | AWARENESS WORKSHOPS
Selection and appointment of a competent Service Provider approved
by the principal agent, provision of a Service Provider Workshop
Plan and a suitable venue, conducting of awareness workshops by
means of traditional and/or modern multi-media techniques, including
follow-up courses, making available all tuition material and performing
assessment procedures, all in accordance with the HIV/AIDS
Specification
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
102 | C10.3 | POSTERS, BOOKLETS, VIDEOS, ETC.
Provision, displaying, maintaining and replacing, when necessary, of
four plastic laminated posters, booklets and educational videos, etc.
for the duration of the construction period, all in accordance with the
HIV/AIDS Specification
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
103 | C10.4 | ACCESS TO CONDOMS
Provision and maintenance of condom dispensers fixed in position,
including male and female condoms, replenishing male and female
condoms daily as required for the duration of the construction
period, all in accordance with the HIV/AIDS Specification
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
104 | C10.5 | MONITORING
Monitoring HIV/AIDS awareness of workers, providing the principal
agent with access to information including making available all
reports, thoroughly completed and reflecting the correct information,
for the duration of the construction period and close out, all in
accordance with the HIV/AIDS Specification
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  | Page No.
NO | REFERS | [5 empty] | AMOUNT
TO
105 | C11.0 | OCCUPATIONAL HEALTH AND SAFETY ACT
The contractor shall comply with all the requirements set out in the
Construction Regulations, 2003 issued under the Occupational Health
and Safety Act, 1993 (Act No 85 of 1993)
It is required of the contractor to thoroughly study the Health and
Safety Specification that must be read together with and is deemed
to be incorporated under this Section of the bills of quantities / lump
sum document
The contractor must take note that compliance with the Occupational
Health and Safety Act, Construction Regulations and Health and
Safety Specification is compulsory. In the event of partial or total
non-compliance, the principal agent, notwithstanding the provisions
of clause A31.0 of Section A or any other clause to the contrary,
reserves the right to delay issuing any progress payment certificate
until the contractor provides satisfactory proof of compliance. The
contractor shall not be entitled to any compensation of whatsoever
nature, including interest, due to such delay of payment
Provision for pricing of the Occupational Health and Safety Act,
Construction Regulations and Health and Safety Specification is
made under this clause, and it is explicitly pointed out that all
requirements of the aforementioned are deemed to be priced
hereunder and no additional claims in this regard shall be entertained
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
PPE
106 | C11.1 | HI-VISIBILTY CONTI-SUIT
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
107 | C11.2 | HI-VISIBILTY T-SHIRTS
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
108 | C11.3 | STEEL TOE-CAPPED SAFETY BOOTS
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
109 | C11.4 | HI-VISIBILITY SAFETY VEST
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
110 | C11.5 | SABS APPROVED HARD HAT
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  | Page No.
NO | REFERS | [5 empty] | AMOUNT
TO
111 | C11.6 | HI-VISIBILITY RAIN SUITS
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
112 | C11.7 | STEEL TOE CAPPED GUMBOOTS
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
113 | C11.8 | DUST MASKS (STIPULATE FFP)
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
114 | C11.9 | SAFETY GLASSES
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
115 | C11.10 | GLOVES (STIPULATE TYPE):
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
116 | C11.11 | SAFETY HARNESSES
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
117 | C11.12 | ISSUE OF DISPOSABLE GLOVES
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
118 | C11.13 | ISSUE OF FACE SHIELDS
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
119 | C11.14 | OTHER
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
120 | C11.16 | SAFETY REPRESENTATIVE TRAINING
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  | Page No.
NO | REFERS | [5 empty] | AMOUNT
TO
TRAINING
121 | C11.17 | FIRST AIDER TRAINING
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
122 | C11.18 | FIRE FIGHTING TRAINING
Annual/ As required or needing replacing
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
WORKING AT HEIGHTS
123 | C11.19 | BASIC FALL ARREST (US229998)
Once off or every 3 years
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
124 | C11.20 | BASIC FALL ARREST AND RESCUE
(US229995 AND US229998)
Once off or every 3 years
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
125 | C11.21 | FALL PROTECTION PLANNER
(US229998 AND 229994)
Once off or every 3 years
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
SCAFFOLDING (AS PER SANS10085)
126 | C11.22 | SCAFFOLDING SUPERVISOR
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
127 | C11.23 | SCAFFOLDING INSPECTOR
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
128 | C11.24 | SCAFFOLDING ERECTOR
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
129 | C11.25 | OTHER
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  | Page No.
NO | REFERS | [5 empty] | AMOUNT
TO
HEALTH AND SAFETY SALARIES
130 | C11.26 | CHC MANAGER
Monthly Salary
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
131 | C11.27 | CHC OFFICER
Monthly Salary
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
132 | C11.28 | OTHER
Monthly Salary
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
SPECIFIC HEALTH AND SAFETY ITEMS
133 | C11.29
Pre-placement, Annual and Exist
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
134 | C11.30 | SPILL KIT
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
135 | C11.31 | ACCOMMODATION OF TRAFFIC
Accommodation of Traffic as per Client tender BOQ
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
136 | C11.32 | INDUCTIONS
Annual
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
137 | C11.33 | FIRST AID KITS
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
138 | C11.34 | FIRE EXTINGUISHERS
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
139 | C11.35 | ABLUTIONS
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  | Page No.
NO | REFERS | [5 empty] | AMOUNT
TO
140 | C11.36 | BARRIER NETTING
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
141 | C11.37 | FALL PROTECTION PLAN
Fall Protection Plan drafted by a Fall Protection Planner US22994
and 229998 (once off and ongoing implementation)
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
142 | C11.38 | NON-TOUCH THERMOMETER
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
143 | C11.39 | HAND SANITIZER
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
144 | C11.40 | BIOHAZARD BINS AND DISPOSAL
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
145 | C11.41 | OTHER
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
SAFETY SIGNAGE
146 | C11.42 | CONSTRUCTION BOARDS
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
147 | C11.43 | FIRE EXTINGUISHER
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  | Page No.
NO | REFERS | [5 empty] | AMOUNT
TO
148 | C11.44 | DIRECTIONAL SIGNAGE
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
149 | C11.45 | EMERGENCY ASSEMBLY POINT
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
150 | C11.46 | NO SMOKING SIGNAGE
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
151 | C11.47 | LADIES AND MEN'STOILETS SIGNAGE
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
152 | C11.48 | NO NAKED FLAMES' SIGNAGE
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
153 | C11.49 | OTHER (OTHER SIGNAGE)
Once off
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
SAFETY DOCUMENTATION
154 | C11.50 | HEALTH AND SAFETY PLAN
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
155 | C11.51 | HEALTH AND SAFETY FILE
| Fixed:_________Value related:_________Time related:__________ |  |  | Item
156 | C11.52 | OTHER
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  | Page No.
NO | REFERS | [5 empty] | AMOUNT
TO
In so far as possible, the Contractor is encouraged to expand the
PPGs skills, knowledge and performance levels.
171 | Fixed:_________Value related:_________Time related:__________ |  |  | Item
TENDERER’S TO NOTE CONDITIONS
| a) | The contract to be entered into between the Contractor and
the PPG’s will be a LABOUR ONLY sub-contract.
| b) | The Contractor will be responsible for ensuring that all
materials for use by the PPG’s in the works are to be on site
timeously. The Contractor shall liaise with The Mentor and
PPG to determine the nature and extent of materials
required and the lead time necessary.
| c) | The Contractor shall be responsible for the overall
programming of the Works, and he is to allow for monitoring
the PPG’s programme and progress.
| d) | In conjunction with the Mentor, he is to allow for the
supervision and mentoring (where necessary) of the PPG to
ensure quality and adherence to standard building practice
| e) | The Contractor is to allow for extra storage facilities on site
for the PPG’s tools and equipment.
| f) | Basic tools shall be provided by the PPG’s and where these
are not available; the Contractor will supply him with the
necessary tools and equipment and deduct the costs thereof
from the interim claims made by the PPG.
| g) | Work requiring specialized tools will be provided free of
charge by the Contractor with the provision that these be
returned upon completion of the Work.
CO-ORDINATION
The Contractor is to co-ordinate the work of all the PPG’s,
Sub-Contractors and Nominated Sub- Contractors appointed direct
by the Employer in such a manner and at all times as will suit the
building programme and he is to allow adequate access, for the
PPGs, where required, to carry out their work in an efficient manner as
no claims for extras in this connection will be entertained.
172 | Fixed:_________Value related:_________Time related:__________ |  |  | Item
ATTENDANCE
The Contractor may allow for attendance upon the PPG’s concerned
to execute the work. The Contractor is to allow the PPG’s the use of
any scaffolding belonging to him while it remains so erected on the
site.
Where scaffolding is necessary for the use by any PPG and the
Contractor has not erected any for his own use or has removed same
after his own use, the Contractor shall supply sufficient scaffolding to
the PPG to be erected and dismantled by the PPG and returned to
the Contractor.
This attendance upon PPG’s to execute the work is to include for the
scaffolding provisions as aforesaid and, in addition, is to include for
co-operating to the fullest extent with all the parties, attending on
off-loading materials, providing suitable storage for tools and
materials used by the PPG’s, use of general facilities such as latrines,
etc., supply and cost of power, lighting, water and the like.
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  | Page No.
NO | REFERS | [5 empty] | AMOUNT
TO
173 | Fixed:_________Value related:_________Time related:__________ |  |  | Item
Addtions | Penalties
| (a) | Penalty for failure to comply with contractual |  | Month |  | -3000
requirements
|  | (i) | Failure to maintain valid contract guarantee | Month |  | -3000
|  | (ii) | Failure to have a project Contracts Manager | Days |  | -2000
|  | (iii) | Failure to have site Agent on site | Days |  | -1000
|  | (iv) | Failure to have OHS officer onsite | Days |  | -1000
|  | (v) | Failure to practical completion date | Days |  | -5000
| (b) | Penalty for failure to comply with contractual
reporting requirements (to be submitted 2 days
before progress meeting)
|  | (i) | Progress report | Days |  | -1000
|  | (ii) | OHS report | Days |  | -1000
|  | (ii) | EPWP report | Days |  | -1000
| (c) | Penalty for serious violations:
|  | (i) | Hazardous chemical/oil spill and/or | No |  | -1000
dumping non-approved sites
| (d) | Penalty for less serious violations:
|  | (i) | Littering on site | No |  | -1000
|  | (ii) | Persistent or un-repaired fuel and oil leaks | No |  | -500
|  | (ii) | Excess dust or excess noise emanating | No |  | -1000
from site
|  | (iv) | Possession or use of intoxicating | No |  | -500
substances on site
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to collection
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
1
ITEM | PAYMENT | DESCRIPTION |  | Page No.
NO | REFERS | [5 empty] | AMOUNT
TO
ALTERATIONS
COLLECTION
| Total Brought Forward from Page No. |  |  | 97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL Carried Forward
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | Bill
0 | [6 empty] | 1
ITEM | PAYMENT | DESCRIPTION |  | Page No.
NO | REFERS | [5 empty] | AMOUNT
TO
Bill No. 1 PRELIMINARIES AND GENERAL Brought Forward
126
127
128
BILL No. 1
Bill No. 1 PRELIMINARIES AND GENERAL carried to Summary

## Bill 2
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
2
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL No. 2
ALTERATIONS TO EXISTING BUILDING
| Notes: 1. | Tenderers are advised to study the 'Construction specification
PW371-A and B as amended (downloadable from Department
of Public Works website, www.publicworks.gov.za) before
pricing this bill 2. Unless otherwise stated all items in this Bill
| Notes: 2. | All prices/rates to be net, excluding Value Added Tax
GENERAL NOTES
For further preambles and full descriptions of items not fully described in this Bill,
reference must be made to supplementary preambles and descriptions in the
other Bills of this Section. Such supplementary preambles and descriptions
shall apply equally.
View site
Before submitting his tender the contractor shall visit the site and satisfy himself
as to the nature and extent of the work to be done and the value of the materials
contained in the buildings or portions f the buildings to be demolished. No claim
for any variations of the contract sum in respect of the nature and extent of the
inferior or damaged materials will be entertained
GENERAL
The term "remove" shall be deemed to mean removal from site by the Contractor
to a registered dumping ground located by the Contractor
In taking down and removing existing work the utmost care shall be observed to
prevent any structural or other damage to remaining portions of the building and
the Contractor shall provide all shoring, needling, strutting, etc. to ensure stability
The contractor shall carry out the whole of the works with as little mess and noise
as possible and with a minimum of disturbance to adjoining premises and their
tenants. He shall provide proper protection and provide, erect and remove when
directed, any temporary tarpaulins that may be necessary during the progress of
the works, all to the satisfaction of the principal agent
Water supply pipes and other piping that may be encountered and found
necessary to disconnect or cut, shall be effectually stopped off or grubbed up
and removed, and any new connections that may be necessary shall be made
with proper fittings, to the satisfaction of the principal agent
Doors, fanlights, fittings, frames, linings, etc which are to be re-used shall be
thoroughly overhauled before refixing including taking off,easing and rehanging,
cramping up, re-wedging as required and making good cramps, dowels, etc, and
easing, oiling, adjusting and repairing ironmongery as necessary, replacing any
glass damaged in removal or subsequently and stopping up all nail and screw holes
holes with tinted plastic wood to match timber, unless otherwise described.
Re-painting or re-varnishing is given separately
Prices for taking out of doors, windows, etc shall include for removal of all beads,
architraves, ironmongery, etc
Prices for taking out and removing doors and frames shall include for removing door
stops, cabin hooks, etc and making good floor and wall finishes to match existing
Prices for taking out and removing sanitary fittings shall include the removal of
necessary fitting and making good floor/wall finishes to match existing
With regard to building up of openings in existing walls, cement screeds and
pavings,granolithic, tops of walls, etc, shall be levelled and prepared for raising of
brickwork
Making good of finishes shall include making good of the brick and concrete
surfaces onto which the new finishes are applied, where necessary
The contractor will be required to take all dimensions affecting the existing
buildings on the site and he will be held solely responsible for the accuracy of all
such dimensions where used in the manufacture of new items (doors, windows,
fittings, etc)
BILL No. 2
BILL No. 2 ALTERATIONS carried to collections
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
2
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
Materials arising from the alterations must be carted away to a tip provided by
the contractor and the contractor shall be responsible for paying any tipping fees.
The contractor is strictly advised to visit the site to assess the extent of the
scope and any risks associated with this work because claims for extra payment
arising as a result of the contractor's failure to fully understand the scope and its
risks will not be accepted. All the works must be carried out in compliance with
Occupation Health and Safety Act, Construction Regulations and any other laws
applicable at the time the works are being executed.
NB - Contractor is responsible for accurate on-site order of lengths
TEMPORARY BARRIERS, SCREENS, ETC
Temporary barriers, screens, etc including removal
1 | Allowance for all necessary temporary tarpaulins, barricades,screens, fencing, |  | item | 8
temporary waterproofing, dust proofing, etc required to isolate buildings, walkways,
pavements or any sections under construction including any sections of new or
existing buildings for the purposes of excluding users from the remainder of the
building
REMOVAL OF EXISTING WORK
2 | Allow for protecting all existing work liable to suffer damage (i.e. Walls, finishes, |  | item | 8
floors, windows, etc.) from damage during the building operations, alterations,
etc., and make good all work damaged with new material to match existing to
the approval of the profesional service provider.The contractor shall cover up and
protect from injury all work not removed and shall make good at his own expense
any damage that may occur
Hacking up/off and removing granolithic, screeds, plaster, etc from concrete
or brickwork and preparing surfaces for new screed, plaster, tile finishes, etc
3 | Internal plaster from walls and columns |  | m² | 550
4 | External plaster from walls, columns and beams |  | m² | 100
Hacking up/off and removing tiles including removing mortar bed or adhesive
from concrete or brickwork and preparing surfaces for new screed, plaster,
tile finish, etc
5 | Remove existing floor tiles |  | m² | 450
6 | Remove existing wall tiles |  | m² | 650
Carefully take out and remove existing sanitary fittings, countertops, gutters,
downpipes and associated pipework, including disconnecting services,
removing all redundant materials from site, and making good to affected walls
and floors
7 | Vitreous china wash hand basin |  | No. | 60
8 | Vitreous china WC pan with flush valve and flush pipe |  | No. | 80
9 | Vitreous china wall hung urinal with flush valve and flush pipe |  | No. | 35
10 | Gutters and down pipes |  | m | 20
Taking down and removing roofs, floors, panelling,ceilings, partitions, etc
including making good to receive new
11 | Ceilings |  | m² | 110
Taking out and removing sundry joinery work, fittings, etc
12 | Wall finishes |  | m² | 330
Taking out/off and removing electrical fittings, pipes and wiring including
making good to receive new or pre-existing components that is suitable for
reuse
13 | Removal of all Electrical equipment and fittings |  | No. | 15
14 | Power skirting covering from power skirting bodies |  | m | 80
BILL No. 2
BILL No. 2 ALTERATIONS carried to collections
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
2
Item |  |  |  |  | RATE
No. | DESCRIPTION |  | UNIT | QUANTITY |  | AMOUNT
15 | Reinstatements of all electrical equipment, new lights and any pre-existing |  | No. | 15
components that is suitable for reuse according to the princpal agent
Taking out and removing doors, windows, etc
16 | Door |  | No. | 74
GENERAL MAINTANANCE
Unblocking of existing outside drainage
17 | Drainage |  | No. | 8
18 | Allow provisional Sum |  | Prov sum | 1 | 20000 | 20000
Cleaning floor and preparing screeds for new floor coverings
19 | Concrete floors |  | m² | 434
Cleaning windows
20 | All tiles |  | m² | 907.5
21 | Window glazing |  | m² | 70
ROOF COVERING/STRUCTURE
Examing of existing roof and making good
22 | Examining roofs check for roof leaks, check and fix loose timber trusses, |  | m² | 80
supports, rafters including ridge cappings and securing loose nails, replacing
missing or defective screws and/or nails with 120mm galvanised steel drive
screws, making good holes with approved sealant or waterproofing as
specified by the architect to render watertight and leave in good order
Carefully taking down and removing roofs
23 | Roof and purlin laths while securing existing trusses in place |  | m² | 80
24 | Treat existing trusses measured net with two coats Powafix or similar and |  | m² | 80
approved creosote protective coating
BUILDING UP OPENINGS
Sundries
25 | Cutting and toothing new brickwork to existing |  | m² | 5
Taking out/off and removing glass, mirrors, window frames and preparing to receive
new aluminum windows
26 | Windows |  | m² | 10
BUDGETARY ALLOWANCES
The following Budgetary Allowances are for work to be executed by the
Sub-Contractor or specialist suppliers and priced at Bill rates or rates to be
agreed and to be used as directed by the Principal Agent and to be deducted
in whole or in part if not required
27 | Provide the sum of R20 000.00 (Twenty Thousand) for breaking down/ |  | Prov sum | 1 | 20000 | 20000
demolishing and removing existing structures from rooms and making
partitions lot as directed by architect
BILL No. 2
BILL No. 2 ALTERATIONS carried to collections
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
2
Item |  |  |  |  | RATE
No. | DESCRIPTION |  | UNIT | QUANTITY |  | AMOUNT
COLLECTION
130
Total Brought Forward from Page No.
131
132
BILL No. 2
BILL NO. 2 ALTERATIONS carried to Summary

## Bill 3
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
3
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 3
MASONRY
| Notes: 1. | Tenderers are advised to study the 'Construction specification
PW371-A and B as amended (downloadable from Department
of Public Works website, www.publicworks.gov.za) before
pricing this bill 3. Unless otherwise stated all items in this Bill
| Notes: 2. | All prices/rates to be net, excluding Value Added Tax
SUPPLEMENTARY PREAMBLES
Materials: All bricks, blocks, and masonry units shall comply with the relevant
SANS standards and the approved samples provided by the Principal Agent.
Materials shall be stored on site to prevent contamination, moisture penetration,
or damage
Mortar: Mortar mixes shall be prepared strictly in accordance with the
specification. The Contractor shall ensure correct proportions, mixing, and
consistency. Only clean water shall be used for mixing.
Workmanship: All masonry work shall be executed by skilled masons with
proper tools and equipment. Work shall be true to line and level, with uniform
joints as per specification. Any defective work shall be replaced at the
Contractor’s expense.
Reinforcement and Ties: Where masonry is reinforced or requires wall ties,
these shall be provided as per drawings and specifications. Steel reinforcement
shall be free of rust, oil, and scale before placement.
Proprietary products in descriptions
Proprietary products shall be used as specified. Substitute products of similar
quality and specification may only be used with prior approval by the Principal
Agent
Sizes in descriptions
Where sizes in descriptions are given in brick units, "one brick" shall represent
the length and "half brick" the width of a brick
NB - Contractor is responsible for accurate on-site order of lengths
BRICKWORK
Brickwork of NFP bricks in class II mortar
1 | Half brick walls |  | m² | 15
2 | One brick walls |  | m² | 15
BRICKWORK SUNDRIES
2,5mm Brickwork reinforcement
3 | 75mm Wide reinforcement built in horizontally |  | m | 205
4 | 150mm Wide reinforcement built in horizontally |  | m | 102
Granite/Stone (Off-White Colour) by specialist
5 | Countertop |  | m² | 120
BILL No. 3
BILL NO. 3 MANSONRY carried to Summary

## Bill 4
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
4
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 4
CARPENTRY AND JOINERY
| Notes: 1. | Tenderers are advised to study the 'Construction specification
PW371-A and B as amended (downloadable from Department
of Public Works website, www.publicworks.gov.za) before
pricing this bill 4. Unless otherwise stated all items in this Bill
| Notes: 2. | All prices/rates to be net, excluding Value Added Tax
SUPPLEMENTARY PREAMBLES
Joinery Descriptions of frames shall be deemed to include frames,
transomes, mullions, rails, etc
Descriptions of hardwood joinery shall be deemed to include pelleting
of bolt holes
Fixing Items described as "nailed" shall be deemed to be fixed with
hardened steel nails or shot pins to brickwork or concrete
Decorative laminate finish Laminate finish shall be glued under
pressure. Edge strips shall be butt jointed at junctions with adjacent
similar finish
NB - Contractor is responsible for accurate on-site order of lengths
1 | High Gloss Floating Cabinet (Wood Look) by specialist (2600 x 900 mm) |  | m2 | 100
Built-in Cupboard (BIC) with Lockable Storage
BILL No. 4
BILL NO. 4 CARPENTRY AND JOINERY carried to Summary

## Bill 5
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
5
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 5
CEILINGS,PARTITIONS AND ACCESS FLOORING
| Notes: 1. | Tenderers are advised to study the 'Construction specification
PW371-A and B as amended (downloadable from Department
of Public Works website, www.publicworks.gov.za) before
pricing this bill 5. Unless otherwise stated all items in this Bill
| Notes: 2. | All prices/rates to be net, excluding Value Added Tax
SUPPLEMENTARY PREAMBLES
Items described as "nailed" shall be deemed to be fixed with hardened steel nails
or pins or shot pinned to brickwork or concrete
Items described as "plugged" shall be deemed to include screwing to fibre, plastic
or metal plugs at not exceeding 600mm centres, and where described as "bolted"
the bolts have been given elsewhere
Ceilings
Unless otherwise described ceilings shall be deemed to be horizontal
Bulkheads
Bulkheads are defined as those portions of ceilings which are stepped down from
the general ceiling level in a particular room or area and which generally occur
along the perimeter. Their purpose is either to conceal services or to create
architectural features
Bulkheads have only been described as such where they conform to the above
definition and where the horizontal or vertical dimensions do not exceed 900mm.
Where these dimensions are more than 900mm such portions of ceilings have
been included in the appropriate general items of ceilings
Unless otherwise described bulkheads shall be deemed to be horizontal along the
length
NB - Contractor is responsible for accurate on-site order of lengths
Shadow-Line Ceiling
9,5 mm gypsum plasterboard ceilings with taped joints, finished with a full skim
coat of gypsum plaster trowelled to a smooth polished surface, all in
accordance with the manufacturer’s recommendations.
The system must include all necessary suspension hangers, perimeter trims,
shadow-line profiles, jointing compounds, screws, and accessories for a
complete installation.
Bulkheads are to be constructed in the same finish with suitable framing, corner
trims, and supports.
9.5 mm gypsum plasterboard ceiling/ bulkhead with taped and plastered joints,
smooth polished finish, including suspension system and shadow-line trims
complete.
1 | Ceiling |  | m2 | 260
2 | Bulk Head |  | m2 | 120
BILL No. 5
BILL NO. 5 CEILINGS,PARTITIONS AND ACCESS FLOORING carried to Summary

## Bill 6
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
6
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 6
IRONMONGERY
| Notes: 1. | Tenderers are advised to study the 'Construction specification
PW371-A and B as amended (downloadable from Department
of Public Works website, www.publicworks.gov.za) before
pricing this bill 06. Unless otherwise stated all items in this Bill
| Notes: 2. | All prices/rates to be net, excluding Value Added Tax
SUPPLEMENTARY PREAMBLES
Finishes to ironmongery
Where applicable finishes to ironmongery are indicated by suffixes
in accordance with the following list:
SS Stainless Steel
BS Satin bronze lacquered
CH Chromium plated
SC Satin chromium plated
SE Silver enamelled
GE Grey enamelled
AS Anodised silver
AB Anodised bronze
AG Anodised gold
ABL Anodised black
PB Polished brass
PL Polished and lacquered
PT Epoxy coated
SD Sanded
Unless otherwise stated ironmongery is to be the manufacture's standard
corrosion resistant ironmongery for the particular product ranges.
Installed to Architects specification
Surface finishes should be restricted to polished chrome or satin chrome on all
approved ironmongery for external and internal doors " unless otherwise stated.
NB - Contractor is responsible for accurate on-site order of lengths
LOCK SETS, HANDLES, CYLINDERS, FLUSH BOLTS ETC.
1 | Bathroom thumb-turn and emergency release set manufactured in stainless steel, |  | No | 80
suitable for internal bathroom doors, complete and ready for installation, or
similar and approved
2 | Euro-profile double cylinder lock, sash type, size 2 × 18 mm, complete with three |  | No | 16
(3) keys, suitable for standard Euro-profile lock cases, or similar and approved
3 | Modular backplate, minimum size 152 × 76 mm, suitable for use with Euro-profile |  | No | 16
cylinder locks, complete with fixings, or similar and approved.
BILL No. 6
BILL NO. 6 IRONMONGERY carried to Summary

## Bill 7
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
7
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 7
METALWORK
| Notes: 1. | Tenderers are advised to study the 'Construction specification
PW371-A and B as amended (downloadable from Department
of Public Works website, www.publicworks.gov.za) before
pricing this bill 07. Unless otherwise stated all items in this Bill
| Notes: 2. | All prices/rates to be net, excluding Value Added Tax
Notes for Contractor:
Steel to be S355 mild steel or equivalent, free from rust, mill scale, or defects
All cut ends to be ground smooth and coated with anti-rust primer
Bolts/anchors to be stainless steel or galvanised for durability
Installation must ensure alignment, rigidity, and neat finish.
NB - Contractor is responsible for accurate on-site order of lengths
Stairs, balustarding, cat ladders, grills,gates, framework,etc
1 | 45 x 45 steel angle bolted to wall |  | m | 100
ALUMINIUM WINDOWS
6.38mm thick solorvue grey xhl normal strength glass or similar approved. All glazing
to adhere to the requirements of sans 10400-part N. (opaque) incl. 20mm wide &
5mm thick factory fitted black aluminium flat bars pop riveted into frame to all
opening sections. Spaced a maximum of 100mm between each bar. Powder coated
dust grey vp7121 28mm aluminium frame
2 | 600mm x 900mm high |  | No. | 4
3 | 1800mm x 900mm high |  | No. | 1
4 | 1200mm x 900mm high |  | No. | 1
6 | 1800mm x 1200mm high |  | No. | 1
BILL No. 7
BILL NO. 7 METALWORK carried to Summary

## Bill 8
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
8
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 8
PLASTERING
| Notes: 1. | Tenderers are advised to study the 'Construction specification
PW371-A and B as amended (downloadable from Department
of Public Works website, www.publicworks.gov.za) before
pricing this bill 08. Unless otherwise stated all items in this Bill
| Notes: 2. | All prices/rates to be net, excluding Value Added Tax
SUPPLEMENTARY PREAMBLES
Wall preparation to include grout grinding, levelling and skim coating surface
with new mortar ready to receive new plaster/backing
General
All specialist plaster wall coverings shall be executed in strict accordance with
the manufacturer's instructions
NB - Contractor is responsible for accurate on-site order of lengths
INTERNAL PLASTER
Cement plaster on brickwork, on:
1 | On walls |  | m² | 680
2 | On narrow widths and sloping tops of sills |  | m² | 60
All specialist plaster wall coverings are to be executed in strict accordance
with the manufacturer's instructions
EXTERNAL PLASTER
Cement plaster on brickwork, on:
1 | On walls |  | m² | 60
2 | On narrow widths and sloping tops of sills |  | m² | 6
All specialist plaster wall coverings are to be executed in strict accordance
with the manufacturer's instructions
BILL No. 8
BILL NO. 8 PLASTERING carried to Summary

## Bill 9
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
9
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 9
TILING
| Notes: 1. | Tenderers are advised to study the 'Construction specification
PW371-A and B as amended (downloadable from Department
of Public Works website, www.publicworks.gov.za) before
pricing this bill 09. Unless otherwise stated all items in this Bill
| Notes: 2. | All prices/rates to be net, excluding Value Added Tax
SUPPLEMENTARY PREAMBLES
Fixing
Unless described as "fixed with adhesive to plaster (plaster elsewhere)"
descriptions of tiling on brick or concrete walls, columns, etc shall be deemed
to include 1:4 cement plaster backing and descriptions of tiling on concrete floors
etc shall be deemed to include 1:3 plaster bedding
Tiling described as "fixed with adhesive on power floated concrete" shall be
deemed to include for approved tiling key-coat
Ceramic, porcelain, marble and granite tiles are to be fixed and grouted with
suitable adhesives and grouts products as recommended by the manufacturer
of the tiles
NB - Contractor is responsible for accurate on-site order of lengths
Feature wall only at wash hand basins
Subway Cinque Terre Ocean Glossy Ceramic Wall Tiles 100x300mm CTM
1 | On new Feature walls |  | m² | 150
Network Grey Matt Ceramic Wall Tiles 600x300mm CTM
2 | On walls |  | m² | 700
FLOOR TILING
Hilton Grey Rectified Matt Glazed Porcelain Floor Tiles 600x600mm CTM
3 | On floors |  | m² | 450
BILL No. 9
BILL NO. 9 TILING carried to Summary

## Bill 10
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
10
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 10
PLUMBING AND DRAINAGE
| Notes: 1. | Tenderers are advised to study the 'Construction specification
PW371-A and B as amended (downloadable from Department
of Public Works website, www.publicworks.gov.za) before
pricing this bill 10. Unless otherwise stated all items in this Bill
| Notes: 2. | All prices/rates to be net, excluding Value Added Tax
SUPPLEMENTARY PREAMBLES
Notes for Contractor:
All fittings must be fixed plumb, level, sealed against leaks, and tested. Allow for all
brackets, fixings, silicone sealing, and connection to existing plumbing. Quantities
include only the fittings specified above; no allowance made for additional pipework,
waterproofing, or builder’s work unless noted.
Rates for all piping, fittings, etc. shall include for all fixing in position of fittings,
cutting of chases in brickwork or concrete, excavation of trenches, backfilling, etc.
unless otherwise described
NB - Contractor is responsible for accurate on-site order of lengths
SANITARY FITTINGS
All sanitary fittings to be installed with silicon contact joint
between the fitting and the finished wall, floor or vanity surface
RAINWATER DISPOSAL AND FLASHINGS
New prepainted 200x200mm industrial Gutters with mathcing down pipes
to be installed and designed by speciaist
1 | Grohe trigger spray Tempesta set or similar approved |  | No. | 5
2 | Eastern Toilet (Lecico Neon Squat Pan) with Giberet cistern or similar approved |  | No. | 4
3 | Giberet cisterns |  | No. | 76
4 | Sensea Studio Ceramic Round Freestanding Basin Beige |  | No. | 75
5 | Lacico-Geo Urinal Separator or similar approved |  | No. | 18
Connecting to new water supply points
6 | Connecting new HDPE 25/32mm diameter to water pipes leading into building |  | No. | 8
including all necessary fittings
7 | Provide all necessary testing apparatus, water, materials, etc. and allow for testing |  | Item | 1
water reticulation system to the satisfaction of the Representative. All defective work
shall be taken re-tested until found perfect
BUDGETARY ALLOWANCES
The following Budgetary Allowances are for work to be executed by
the Main Contractor or specialist suppliers and priced at Bill rates or
rates to be agreed.
8 | Provide the sum of R50 000.00 (Fifty Thousand Rand) for the supply, delivery |  | Prov sum | 1 | 50000 | 50000
and installation of fixtures and fittings for toilet, including grab rails,
accessible basin, lever tap, mirror, and associated accessories.
BILL No. 10
BILL NO. 10 PLUMBING AND DRAINAGE carried to Collections
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
10
Item |  |  |  |  | RATE
No. | DESCRIPTION |  | UNIT | QUANTITY |  | AMOUNT
1 | 85mm x 85mm x 0,6mm thick Small Ogee roof gutters |  | m | 130
2 | 75mm x50mm x 0,6mm thick Marble White aluminium downpipe |  | m | 18
3 | Extra over gutter for stopped end |  | No. | 18
4 | Extra over gutter for angle |  | No. | 18
5 | Extra over rainwater pipe for bend |  | No. | 1
6 | Extra over rainwater pipe for shoe |  | No. | 1
SANITARY FITTINGS
All sanitary fittings to be installed with a silicone sealant joint between the
fitting and the finished wall, floor, or vanity surface to ensure a watertight
seal
7 | Gyser |  | No. | 2
8 | TAPS, VALVES, ETC |  | No. | 72
9 | 110mm Pipes |  | m | 60
10 | 50mm Pipes |  | m | 50
BILL No. 10
BILL NO. 10 PLUMBING AND DRAINAGE carried to Collections
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
2
Item |  |  |  |  | RATE
No. | DESCRIPTION |  | UNIT | QUANTITY |  | AMOUNT
COLLECTION
141
Total Brought Forward from Page No.
142
BILL No. 10
BILL NO. 10 PLUMBING carried to Summary

## Bill 11
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
11
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 11
ELECTRICAL WORK
| Notes: 1. | Tenderers are advised to study the 'Construction specification
PW371-A and B as amended (downloadable from Department
of Public Works website, www.publicworks.gov.za) before
pricing this bill 11. Unless otherwise stated all items in this Bill
| Notes: 2. | All prices/rates to be net, excluding Value Added Tax
SUPPLEMENTARY PREAMBLES
The preambles cover the supply, installation, testing, and commissioning of all
electrical works including wiring, light fittings, LED strips, downlights, motion
sensors, hand dryers, and All associated accessories, fixings, supports, and
connections required for a complete installation
RATES
The rates shall include all materials, labour, fixings, supports, connections, testing,
commissioning, and all other incidentals necessary to deliver the electrical
installation in a fully functional, safe, and compliant condition.
NB - Contractor is responsible for accurate on-site order of lengths
1,5mm Twin & Earth
1 | Material |  | m | 201
2 | Labour |  | m | 201
2,5mm Twin & Earth
3 | Material |  | m | 100
4 | Labour |  | m | 100
PVC Conduit
5 | Material |  | m | 150
6 | Labour |  | m | 150
LED Strip lighting (blue, 12–24 V, 8–15 W/m, IP65)
7 | Material |  | m | 150
8 | Labour |  | m | 150
Downlights (6 W, 360 lm min, 2700–3000 K, IP65, 120° beam)
9 | Material |  | No | 80
10 | Labour |  | No | 80
Motion Sensor
11 | Material |  | No | 10
12 | Labour |  | No | 10
Hand dryers - Electric - Automatic - 2,5kW - Stainless Steel
13 | Material |  | No | 16
14 | Labour |  | No | 16
BUDGETARY ALLOWANCES
The following Budgetary Allowances are for work to be executed by
the Main Contractor or specialist suppliers and priced at Bill rates or
rates to be agreed.
15 | Provide the sum of R20 000.00 (Twenty Thousand Rand) for the supply, |  | Prov sum | 1 | 20000 | 20000
delivery and installation of electrical appliances
16 | Allow to carry out installation testing in terms of SANS 10142. Rates to include |  | item | 14
issue of Compliance Certificates for the installation
BILL No. 11
BILL NO. 11 ELECTRICAL WORK carried to Summary

## Bill 12
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
12
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 12
GLAZING
| Notes: 1. | Tenderers are advised to study the 'Construction specification
PW371-A and B as amended (downloadable from Department
of Public Works website, www.publicworks.gov.za) before
pricing this bill 12. Unless otherwise stated all items in this Bill
| Notes: 2. | All prices/rates to be net, excluding Value Added Tax
NB - Contractor is responsible for accurate on-site order of lengths
GLAZING TO FEATURE WALL
Supply and install Oval Black Frame Mirror
1 | 700x500mm CTM or similar approved |  | No. | 72
2 | Custom mirror 2500X400MM |  | No. | 2
BILL No. 12
BILL NO. 12 GLAZING carried to Summary

## Bill 13
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
13
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 13
PAINTWORK
| Notes: 1. | Tenderers are advised to study the 'Construction specification
PW371-A and B as amended (downloadable from Department
of Public Works website, www.publicworks.gov.za) before
pricing this bill 13. Unless otherwise stated all items in this Bill
| Notes: 2. | All prices/rates to be net, excluding Value Added Tax
SUPPLEMENTARY PREAMBLES
DESCRIPTIONS
Descriptions of paintwork shall be deemed to include for all cutting in
PREPARATORY WORK TO EXISTING WORK
Previously painted plastered surfaces shall be thoroughly washed down
with polycell sugar-soap solution, rinse with clean water to remove all
traces of soap, sand glossy surface to a matt finish and allowed to dry
completely for 24 hours before any
Previously painted metal surfaces shall be cleaned of all rust, scale and
dirt, removed by scraping or with steel brushes. All oil and grease shall
be removed and perfectly clean surfaces obtained. If necessary,
the surfaces shall be de-grease
Previously painted wood surfaces shall be thoroughly cleaned down.
Blistered or peeling paint shall be completely removed and cracks and
crevices shall be primed, filled with suitable filler and finished smooth
Contractor shall provide all labor, material, and equipment and perform all
operations necessary for all painting work specified including the painting of
concrete block walls, Drywall partitions, Celings, floors, and exposed iron and
steel work including miscellaneous metal (where applicable)
NB - Contractor is responsible for accurate on-site order of lengths
PAINT ON PLASTER, ETC
Apply one (1) coat sealer/undercoat and two (2) finishing coats of
high-quality acrylic PVA paint to prepared surfaces, or similar and approved
1 | Internal walls, columns, beams, and similar plastered surfaces |  | m² | 1074
2 | External plastered wall surfaces |  | m² | 100
Prepare surfaces and apply two (2) coats gypsum plaster skim to achieve a
smooth and level soffit finish, followed by one (1) coat acrylic undercoat and
two (2) coats premium acrylic matt finish paint, all strictly in accordance with
the manufacturer’s instructions
WOOD SURFACES
Apply one (1) coat oil-based wood primer and two (2) coats polyurethane
enamel paint to prepared timber surfaces, or similar and approved
3 | Fascia boards, dry walls, timber cladding, and similar timber elements. |  | m² | 60
4 | Doors. |  | No. | 160
BILL No. 13
BILL NO. 13 PAINTWORK carried to Summary

## Bill 14
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
14
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 14
SEWER RETICULATION
SUPPLEMENTARY PREAMBLES
uPVC pipes and fittings
Soil, waste pipes of 63mm diameter and greater shall have sockets and spigots
with push-in type integral rubber ring joints. Bends shall be PVC-U fittings all with
similar push-in type joints
Exposed concrete surfaces
Exposed surfaces of concrete storm water channels, cover slabs, inspection eye
marker slabs, gulley tops, cleaning eye tops, catch pits, inspection chambers, etc.
shall be finished smooth with plaster.
Nature of ground
The tenderer must acquaint himself of the presence and depth of subterranean
water and allow therefore in his prices.
Laying, backfilling, bedding, etc. of pipes
Pipes shall be laid and bedded and trenches shall be carefully
backfilled in accordance with manufacturers' instructions.
Where no manufacturer's instructions exist pipes shall be laid in accordance with
Clauses 5.1 and 5.2 of each of the following:
SABS 1200 L: Medium pressure pipelines
LD: Sewers
LE: Storm water drainage
Pipe trenches, etc shall be backfilled in accordance with Clauses 3, 5.5, 5.6, 5.7
and 7 of SANS 1200 DB: Earthworks
(Pipe trenches) Pipes shall be bedded in accordance with Clauses 3.1 to 3.4.1,
5.1 to 5.3 and 7 of SANS 1200 LB: Bedding
(Pipes) Unless otherwise described bedding of rigid pipes shall be Class B
bedding.
Bedding must be selected granular material (specify SABS 1200 LB class B
material) minimum 100mm think on top and bottom of pipe compacted to
90% MDD. Selected fill blanket according to SABS 1200LB; selected fill material
shall be material that has a PI not exceeding 6 and that is free from vegetation
and from lumps or stone of diameter exceeding 30mm. In 150mm layers
compacted to 90% MDD.Fill blanket is above the bedding and 200mm thickness.
In 150mm layers compacted to 90% MDD.
General
Descriptions of pipes laid in and including trenches and of inspection chambers,
catchpits, etc shall be deemed to include excavation, bedding, selected
backfilling material, risk of collapse, working space, compaction to a minimum of
95% MDD density in layers of 150mm and disposal of surplus material on site
surfaces onto which the new finishes are applied, where necessary
The contractor will be required to take all dimensions affecting the existing
buildings on the site and he will be held solely responsible for the accuracy of all
such dimensions where used in the manufacture of new items (doors, windows,
fittings, etc)
Materials arising from the alterations must be carted away to a tip provided by
the contractor and the contractor shall be responsible for paying any tipping fees.
The contractor is strictly advised to visit the site to assess the extent of the
scope and any risks associated with this work because claims for extra payment
arising as a result of the contractor's failure to fully understand the scope and its
risks will not be accepted. All the works must be carried out in compliance with
Occupation Health and Safety Act, Construction Regulations and any other laws
BILL No. 14
BILL No. 14 SEWER RETICULATION carried to collections
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
14
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
applicable at the time the works are being executed.
NB - Contractor is responsible for accurate on-site order of lengths
uPVC Class 34 pipes with socketed joints
| 110mm uPVC Class 34 sewer drainage pipes (pipes complete with |  | m | 28
couplings, spigots, sockets, fittings, adapters, etc,) laid in trenches
not exceeding 1000m deep including all sockets, fittings, adapters,
dpc, excavation, bedding, stone filling, backfilling and compaction
and disposal of surplus material
Extra over uPVC Class 34 pipes for fittings in trenches
|  |  | No | 10
110mm Bend
|  |  | No | 6
110mm Junction
|  |  | No | 5
110 x 75m Reducing junction
Excavate and Build Manholes
| Excavate in compacted earth for and build pre-cast concrete manhole with |  | No | 1
560mm diameter Class B125 Polyester Resin or Type 4 concrete manhole
cover and frame. Manhole with 1000mm internal diameter shaft with 75mm
reinforced concrete wall spacer rings internally, 1110 x 1110mm x minimum
150mm thick cast in-situ concrete slab 25MPa with reinforcement, HDPE
steps 300c/c vertical and horizontal, 20mm Dolomitic steel floated benching
to top of concrete base, 25MPa concrete haunching 100mm wide,
including leaving or forming opening in precast concrete wall for 150mm
diameter outlets including all excavations, backfilling, compaction, working
space, de-watering, risk of collapse, formwork, formwork, reinforcing, etc.
not exceeding 1500 mm deep.
| Extra over excavation in earth for pipe trenches, chambers, etc for excavation |  | m³ | 3
in hard rock
Connection
| Excavate, carefully create opening in existing sewer manhole exceeding |  | No | 1
3000mm not exceeding 4000mm deep, connect new sewer pipe with fittings
and make good
Septic Tank Connection
| Carefully open up existing septic tank, connect new sewer pipe with fittings |  | No | 1
and make good
| Provide all necessary testing apparatus, water, materials, etc. and allow for |  | Item | 1
testing of drainage system to the satisfaction of the Representative. All
defective work shall be taken out and replaced at the Contractor's expense
and the whole re-tested until found perfect
BUDGETARY ALLOWANCES
The following Budgetary Allowances are for work to be executed by
Main Contractor or specialist suppliers and priced at Bill rates or the
rates to be agreed and to be used as directed by the Principal Agent
and to be deducted in whole or in part if not required
| Provide the sum of R20 000.00 (Twenty Thousand Rands) for additional |  | Prov Sum |  |  | 20000
general work still to be designed and will/may be carried out by the contractor
BILL No. 14
BILL No. 14 SEWER RETICULATION carried to collections
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
14
Item |  |  |  |  | RATE
No. | DESCRIPTION |  | UNIT | QUANTITY |  | AMOUNT
COLLECTION
147
Total Brought Forward from Page No.
148
BILL No. 14
BILL NO. 14 SEWER RETICULATION carried to Summary

## Bill 15
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  | Bill
15
Item | DESCRIPTION |  |  |  | RATE
No. |  |  | UNIT | QUANTITY |  | AMOUNT
BILL NO. 15
ROOF COVERINGS
| Notes: 1. | Tenderers are advised to study the 'Construction specification
PW371-A and B as amended (downloadable from Department
of Public Works website, www.publicworks.gov.za) before
pricing this bill 15. Unless otherwise stated all items in this Bill
| Notes: 2. | All prices/rates to be net, excluding Value Added Tax
SUPPLEMENTARY PREAMBLES
DESCRIPTIONS
Descriptions of paintwork shall be deemed to include for all cutting in
PREPARATORY WORK TO EXISTING WORK
Proprietary products shall be used as specified. Substitute products of similar
quality and specification may only be used with prior approval by the Principal
Agent
Fixing
Fixing shall be done according to SABS 1200HB with minimum 225mm end
laps
Guarantee
The contractor will be required to provide a written guarantee, stating that :
1. The roof sheeting is of the specified thickness
2. The client is indemnified against any defects, including colour deterioration
for a minimum period of 15 years
NB - Contractor is responsible for accurate on-site order of lengths
ROOF SHEETING
Roofing sheeting shall be a concealed-fix profile, roll-formed in continuous
lengths from certified steel roof sheeting with a minimum coating mass of
Z200 and a nominal thickness of 0.58 mm, complying with relevant South
African standards, or similar and approved
Roof sheeting shall be fixed to steel or timber purlins and/or girts using
approved concealed-fix clips suitable for the specified sheeting material
(aluminium clips to be used in conjunction with aluminium sheeting where
applicable) and Class 3 corrosion-resistant fasteners.
Installation shall be carried out strictly in accordance with the manufacturer’s
latest specifications and details by an approved and experienced roofing
contractor.
Upon completion and following manufacturer inspection and approval of the
installed roof, a written five-year guarantee for water-tightness shall be
provided.
1 | Roof covering with pitch not exceeding 25 degrees |  | m² | 80
BUDGETARY ALLOWANCES
The following Budgetary Allowances are for work to be executed by
Main Contractor or specialist suppliers and priced at Bill rates or the
rates to be agreed and to be used as directed by the Principal Agent
and to be deducted in whole or in part if not required
2 | Provide the sum of R20 000.00 (Twenty Thousand Rands) for additional |  | Prov Sum |  |  | 20000
general work still to be designed and will/may be carried out by the contractor
BILL No. 15
BILL NO. 15 ROOF COVERINGS carried to Summary

## BOQ - Summary
CONTRACT NUMBER: |  | UPGRADES TO VARIOUS ABLUTION FACILITIES AT THE KIRSTENBOSCH NATIONAL BOTANICAL GARDEN |  |  |  |  | SUMMARY
|  | DESCRIPTION |  | UNIT | QUANTITY | RATE | AMOUNT
BILL NO. 1 |  |  | PRELIMINARIES AND GENERAL
BILL No. 2 |  |  | ALTERATIONS TO EXISTING BUILDING
BILL NO. 3 |  |  | MASONRY
BILL NO. 4 |  |  | CARPENTRY AND JOINERY
BILL NO. 5 |  |  | CEILINGS,PARTITIONS AND ACCESS FLOORING
BILL NO. 6 |  |  | IRONMONGERY
BILL NO. 7 |  |  | METALWORK
BILL NO. 8 |  |  | PLASTERING
BILL NO. 9 |  |  | TILING
BILL NO. 10 |  |  | PLUMBING AND DRAINAGE
BILL NO. 11 |  |  | ELECTRICAL WORK
BILL NO. 12 |  |  | GLAZING
BILL NO. 13 |  |  | PAINTWORK
BILL NO. 14 |  |  | SEWER RETICULATION
BILL NO. 15 |  |  | ROOF COVERINGS
SUBTOTAL
10% CONTIGENCY
TOTAL
ADD 15% VAT
TOTAL PROJECT CONSTRUCTION COSTS